## Slide 1: Deployed RF Antennas for GPS-denied Optimization and Environmental Navigation
Dawson Beatty, Christian Carmack, Jeremy Fie,
Chris Greer, Ross Kloetzel, Jack Maydan,
Kyle Nieukirk, Virginia Nystrom, Amanda Siirola,
Ryan Stewart, Luke Tafur, Ivan Yurkin
Manufacturing Status Review

## Slide 2: Project Overview
Project Overview
Schedule
Budget
Hardware
Software
Electronics

## Slide 3: Project Purpose
Imagine a rover with an objective to explore a remote location, such as Martian deserts or urban canyons
Methods of Navigation:
  GPS
  Landmarks
  Odometry
The DRAGON team pursues a solution using deployed RF beacons as an in-situ GPS network to correct inertial error
High Error

## Slide 4: Specific Objectives
The DRAGON team will provide a fully autonomous method to navigate an unmanned rover in GPS-denied environments with 1m accuracy
This will be done by developing:
  Pods which contain RF-Localization beacons.
  Deployment mechanism to deploy pods to software-determined locations
  Software to determine absolute position and navigate to waypoints
The pods will also have the demonstrational ability to collect and transmit environmental data.

## Slide 5: CONOPS
1 | Upload Mission Information Package |  | 
2 | Collect GPS Truth Position |  | 
3 | Generate Path |  | 
4 | Generate Pod Locations |  | 
5 | Deploy 3 Anchor Pods |  | 
6 | Deploy & Map Pods | or | Move & Localize Rover
7 | Repeat 6 Until Final Waypoint |  | 
MIP
Terrain Map
Waypoints
Obstacles
Mission Planning
Mission Execution
A
B
C

## Slide 6: Levels of Success
 | Level 1 | Level 2 | Level 3
Rover Navigation | Localize rover to 1m with pod array for a 15m user-controlled path. | Correct rover position to 1m with closed-loop error correction. | Autonomously navigate SW-L1 path to within 1m of all 5-10 waypoints.
Pod Deployment | Pods are hand placed, in analytically predetermined locations. | Deploys pod to range > 10m. Internal electronics function after impact. | Rover software calculates trajectories and commands to deploy.
Scientific Data |  | Pods record pressure, temperature, and acceleration data. | Pods collect environmental data at 5 minute frequency.
Pod | Pods provide RF ranging measurements to the rover. | Pods communicate amongst themselves using a mesh network. | Pods toggle between high and low power modes.
Software | Find path for rover to reach 5-10 waypoints avoiding obstacles. | Software determines pod placement for best RF-ranging | Pod placement software balances best science and best RF-ranging.
Verified on Rover
Verified on Laptop
 | Level 1 | Level 2 | Level 3
Rover Navigation | Localize rover to 1m with pod array for a 15m user-controlled path. | Correct rover position to 1m with closed-loop error correction. | Autonomously navigate SW-L1 path to within 1m of all 5-10 waypoints.
Pod Deployment | Pods are hand placed, in analytically predetermined locations. | Deploys pod to range > 10m. Internal electronics function after impact. | Rover software calculates trajectories and commands to deploy.
Scientific Data |  | Pods record pressure, temperature, and acceleration data. | Pods collect environmental data at 5 minute frequency.
Pod | Pods provide RF ranging measurements to the rover. | Pods communicate amongst themselves using a mesh network. | Pods toggle between high and low power modes.
Software | Find path for rover to reach 5-10 waypoints avoiding obstacles. | Software determines pod placement for best RF-ranging. | Pod placement software balances best science and best RF-ranging.

## Slide 7: FBD

## Slide 8: Deployment Module Design
Front View
Side View
20”
17”
10”
30”

## Slide 9: Pod Structure Design
Pod structure contains the ranging electronics: deployed from cannon
Contains batteries in tail for power, electronics are potted for resilience.
Tail
Stability
Landing Orientation
Fuselage: Holds electronics
Foam Nose: Impact crumple zone
95mm
220mm

## Slide 10: Pod Electronics Design
Capabilities:
  Pod to Pod Ranging
  Environmental data (pressure, temperature, and altitude)
  Accelerometer data (+/- 100g’s)
  SD card writing (Environmental and Accel. data)
Dragon Egg Shield [6cm x 6cm]

## Slide 11: Navigation Software Design
Subsystem Goals:
  Generate closed-loop path for rover through waypoints while avoiding obstacles
  Communicate with pod mesh network
  Use pod ranging data to algorithmically correct odometry error (gSLAM) and correct path deviance using onboard control

## Slide 12: Critical Project Elements
CPE | Manufacturing Status
State Estimation | Verified with Rover/Pod Data Integrating in ROS on Rover
Path Following | Verified in ROS with Customer MIP Testing on Rover
RF Ranging | Verified Mesh Network Ranging on Rover Testing Environmental Data Transfer on Rover
Spring Cannon | Completed training Received raw materials Machining gear
Pod Storage & Reload | Tested motor software Machining support structure
Pod Structure | Assembled 1 pod according to manufacturing plans Validating pod design

## Slide 13: Schedule
Project Overview
Schedule
Budget
Hardware
Software
Electronics

## Slide 14: Gantt Chart
Complete
In Progress
May Use Margin
Expected on Time
Removed Task
Critical Task
Here

## Slide 15: Electronics
Project Overview
Schedule
Budget
Hardware
Software
Electronics

## Slide 16: PCB Status
Unpopulated
Populated without processor
Fully Populated
Challenges:
Placing the 3 x 3 x 1 mm3 accelerometer to prevent shorting
  Solution: Stencil and Pick-and-Place to also allow for more precise and controlled placement of solder and sensor
Notes: Amanda

## Slide 17: PCB Manufacturing Plan
Summary:
PCB Revisions complete
Third PCB Revision unnecessary
Populating will begin once procured parts arrive
Brunt of work will come from populating boards
Completion of PCB’s is necessary for pod structure and deployment
Notes: Amanda

## Slide 18: Deployment Control Motors
Summary:
Verify 24V DC motor will rotate exactly once
Implement safety interrupts
Reset step count for azimuth control and rotate to commanded location
Challenges:
Poor part documentation led to additional work for wiring and pinouts
Time Remaining:
16 hrs

## Slide 19: Hardware
Project Overview
Schedule
Budget
Hardware
Software
Electronics

## Slide 20: Cannon Manufacturing Plan
CNC | Time Remaining
Canon Support (x2) | 8 hr
Shaft Support | 6 hr
Mills/Lathes/ Saws | Time Remaining
Reload Support (x2) | 6 hr
Clevis Pin (x2) | N/A
Rack Support | 3 hr
Narrow Rack Support | 3 hr
Launch plate | 3 hr
Base plate | 4 hr
Gear Shaft | N/A
Shaft Adapter | 6 hr
Acrylics/ Plastics | Time Remaining
Funnel | 3 hr
Reloading Guard | 3 hr
Foundation Sheet | 2 hr
Motor Stand (x2) | 6 hr
COTS | Time Remaining
Bevel gears | N/A
Gear rack | N/A
Gear drive train | N/A
Lazy susan | N/A
Shaft Adapter | N/A
PVC barrel | 0.5 hr
Not started | In Progress | Completed/ Delivered
Summary:
Completion Deadlines:
  Machined Parts: Feb 15
  Plastics and Acrylics: Feb 22
  Part Integration: March 1
Challenges
Shop availability and schedule conflicts
Notes: What parts are being manufactured vs. purchased, what is involved in their manufacture, where and how they are being manufactured.
I could color code this slides as well

## Slide 21: Cannon Manufacturing Status
4 team members have completed first two tutorials
All metals have been obtained
Legend
Cots
Currently Manufacturing
Not Started
Completed
Reloading Belt
Reloading Support
Launch
Plate
Rack Support
Gear Shaft
Narrow Rack Support
Notes: Tried to break out parts that couldn’t be seen

## Slide 22: Pod Manufacturing Plan
COTS, mod
Boom: Dowel cut
Potting Tray: Add holes to hobby box for ports, mount switches
Fuselage: Cut tube,
make slots using bandsaw, drill press, and hand tools
Nose: Expanding foam
cots/3dp ‘cupcake tray’
Can produce sixteen
copies in:
10 hours
Laser Cut
Polycarbonate Sheets Procured
Battery springs from cots
Can produce sixteen copies in:
30 min
3D Printed
Material available on campus
Designs to be finalized post testing, no major changes anticipated
Determining necessary printer fill
Can produce sixteen copies in:
2 weeks (6hrs/each)
Where: ITLL
Status:
Power system = built and tested
Potting = drop tested
RF Interference = proven non-issue
Notes: What parts are being manufactured vs. purchased, what is involved in their manufacture, where and how they are being manufactured.
I could color code this slides as well

## Slide 23: Pod Manufacturing Status
Forward work:
One pod built, perform additional testing and validation
Update manufacturing procedures
Continue printing, prep subassemblies
Plan 1-2 full team assembly-line sessions
Challenges:
Demonstrating compatibility with deployment mechanism
  Sub-to-Sub requirements on dimensions/mass
Fatigue/life cycle testing
  Perform multiple drop tests, additional throwing of pod at anticipated range/angle
Once confident in final pod performance, sixteen pod production requires:
26 person-hours
divide by number of team members
Notes: Ivan

## Slide 24: Software
Project Overview
Schedule
Budget
Hardware
Software
Electronics

## Slide 25: Navigation Software Status
Next Steps:
  Test completed blocks on rover
Challenges:
  Working in rover’s unfamiliar programming environment
Expected Time to Completion:
20 Hours

## Slide 26: Pod Software
Status:
All Pod Software is written with most of it verified on the rover
Need to test sleep mode over a full mission duration using the rover
Challenges:
Lack of debug environment makes software development difficult
Testing more than 4 pods is incredibly difficult with a lack of mobile power sources
Overcoming Challenges:
Piecewise software development mitigates difficulty
Using multiple people to test a multipod setup with the rover
Notes: Ivan

## Slide 27: Integration Plan
Challenge: Time, shop access
Estimated Work:
55 hours machining
10 hours assembly
Challenge: Validating  mass producing
Estimated Work:
2 weeks for printing
26 hours to build all
5 hours for testing
Cannon
Pod Structure
Interface Complete. Verified with Rover.
Pod Software
Challenge: Unfamiliar rover user interface
Estimated Work:
10 hour for main
10 hours for functions
Navigation Software
Ready for Full System Testing
Challenge: Combining different software pieces software into main function
Estimated Work:
15 hour testing main
10 hours testing functions
Software + Rover
Challenge: Consistency and fatigue testing
Estimated Work:
1hr potting per board (x14)
Challenge: Fit checks and tolerance stack up
Estimated Work:
2 hours for fit checks
1 hour for final install
Electronics + Pod
Cannon + Rover
65 Hours
20 Hours
43 Hours
Challenge: Placing small accelerometer
Estimated Work:
12 hours to populate PCBs
Pod Electronics
42 Hours
Subsystem Integration
by March 11
System Integration
by March 29
Notes: 166 Hours Until Ready for Full System Testing

## Slide 28: Budget
Project Overview
Schedule
Budget
Hardware
Software
Electronics

## Slide 29: Budget
Total Spent: | $2991.58
Expected Total of Project: | $3999.29
Margin: | $695.62
Extra: | $305.09
 | $5000.00
*Notes:
Budget based on estimated 12 pods + 4 pods for prototyping
Jackal Rover provided by customer
Notes: * Status of all procurements (color code: parts received, pending, and planned)
* Highlight parts with long-lead and most important parts to project success.
* Highlighting uncertainties and corresponding budget margins

## Slide 30: Budget
Parts with Long Lead Times:
Motor Driver
Gear Rack
Time Belts and Pulleys
Brush Motors
Custom PCB Boards
(All long lead time components have arrived)
Critical Parts:
Custom PCB Boards
(In transit)
Blue Pills and RF Modules
Pod Structure (Not ordered)
Motor Driver
Gear Rack
Deployment Structure
24V DC Brush Motor
Stepper Motors (1 of 2 received)
POD SUBSYSTEM
DEPLOYMENT SUBSYSTEM
Parts Received
Parts Ordered (In Transit)
Parts Partially Received
Parts yet to be Ordered
Notes: * Status of all procurements (color code: parts received, pending, and planned)
* Highlight parts with long-lead and most important parts to project success.
* Highlighting uncertainties and corresponding budget margins
How have we saved money:( I originally planned for a worst case scenario) Money saved by not doing third PCB revision, cheaper to buy blue pill than STM32 processors, deployment finding different company to purchase base plate to say money, reusing components during PCB testing (and buying the support components in bulk at once), minimizing shipping as much as possible, custom PCB through Osh Park rather than Advanced circuits which was originally planned.

## Slide 31: Deployed RF Antennas for GPS-denied Optimization and Environmental Navigation
Thank you for your time --
Come check out our testing progress at TRR!
Manufacturing Status Review

## Slide 32: Appendix

## Slide 33: A: Schedule

## Slide 34: Gantt: Software & Electronics

## Slide 35: Gantt: Manufacturing

## Slide 36: Gannt: Assembly & Integration

## Slide 37: Gantt: Deliverables

## Slide 38: B: Team Organization

## Slide 39: Organizational Chart: 09/18 – 02/19
4 Team Members
Progress: On Track
5 Team Members
Progress: Falling Behind
3 Team Members
Progress: Ahead of Schedule

## Slide 40: Organizational Chart: 03/19 – 05/19
* Pod Electronics Team moves to Deployment Team when their integration tasks are complete
4 Team Members
Progress: On Track
8 Team Members
New team members assist with motors & pod assembly
0 Team Members
PCB Complete
Pod SW Complete

## Slide 41: C: Safety

## Slide 42: Deployment Module Design: Safety
Purpose:
  Establish deployment readiness state for safe pod deployment and abort
Design:
State | Description | Steps to abort | Notes
1 | Pod in tube, electrical inhibit OUT, spring compressing | Send software stop Send software command to reverse motor direction Proceed from State 2.2 | Front of rover clear at all times
2 | Pod in tube, electrical inhibit OUT, spring uncompressed | Send software stop Place electrical inhibit IN Remove pod from tube | Front of rover clear until after step 2
3 | No pod in tube, electrical inhibit OUT, spring uncompressed | Place electrical inhibit IN | 
4 | No pod in tube, electrical inhibit IN, spring uncompressed | None | Transport rover in this state. Safe state to unload tube.
*Azimuth control occurs between State 1 and 2. State 2 is considered fire-ready and full safety measures are to be in place.

## Slide 43: Safety Status
Component | Time Remaining | Notes
Software stop from serial command | -- | Completed
Reverse motor direction from serial command | -- | Completed
Software stop from PS4 controller | 5 hrs | To be started: 2/18
Reverse motor direction from PS4 controller | 1 hr | To be started: 2/18
Electrical Inhibit | 5 hrs | To be started: 2/25

## Slide 44: D: Pod Structure

## Slide 45: Integration: Pod Structure
All joints bonded with epoxy, sufficient strength due to majority of stress being compressive
Green: Laser Cut
Red: 3D Printed
Blue: COTS, modified
A
B
A - Removable hardware for battery swap
B - Friction rotation slot-lock for electronics access, can pin if needed
Notes: Ivan
mention batteries in tail
fuselage is where electronics are housed
foam crumple zone for impact

## Slide 46: Potting 1
Sylgard-184 potting material was used to test pot two processor boards
Drop test performed and post functionality validated
Procedure written with steps and lessons learned
Custom 3D printed housing modeled using latest boards
Will move to potting full custom PCB when enough are available for ‘one to go missing’.
Larger board and shield config should be stronger

## Slide 47: Potting 2

## Slide 48: Pod Structure: Manufacturing Status
Once confident in final pod performance, sixteen pod production requires:
26 person-hours
divide by number of team members
Forward work:
Test and validate pod, update written manufacturing procedures
Plan 1-2 full team assembly-line sessions
  Parts will be prepped in advance, assembled using updated procedures
Parts | Time (conservative) | Quantity | Totals
Laser Cut Parts | 30 min | 1 | 30 min
Custom 3D Prints | 6hrs | 15 | 3 days nonstop, est ~2 wk
COTS Tail Boom & Fuselage | 5 min | 30 | 150 min
COTS Nose and Potting | 1hr | 8 | 480 min
Assembly For Whole Pod | 1hr | 16 | 960 min
Challenges:
Demonstrating compatibility with deployment mechanism
Fatigue testing
Notes: Ivan

## Slide 49: E: Integration

## Slide 50: Integration Plan
Navigation Software to Rover: Most algorithms written, to be ported over before TRR
  Progress already made on porting some earlier versions of software
Deployment Mech to Rover: Deployment Mech operates independently using its own microcontroller, rover SW to send serial r/w commands
  This interface is the same as rover-to-pod, which is complete
Pod Electronics to Pod: The PCB will be potted using NASA 8739-1b, the potting tray will be epoxied to fuselage base
Pod to Deployment Mech: Pods will installed, reloaded, and deployed
  This is a basic mechanical interface which requires mass property and fit checks, 1-3 pods will be produced in advance if necessary for deployment testing, sub-to-sub requirements were previously drafted to ensure dimensional compliance