## Slide 1: Manufacturing Status Review
Justin Alvey Ryan Bennett Emma Cooper
Sean Ellingson Pierre Guillaud Nash Jekot
Jacob Killelea Micah Svenson Kendall Worden
Optical Thermal Regulation System
Customer: General Atomics Advisor: Dr. Kathryn Wingate

## Slide 2: Project Overview

## Slide 3: Baseline Design
Goal: Replace traditional temp sensors with IR camera
System uses 2 cameras mounted on bay ceiling/floor (shown in green)
Image centrally located electronics stack and return surface temperature data
Turn representative indicators on/off based on localized temperature hot spots
TestBed replicates materials and dimensions of the stack with modifications to allow changing of some parameters.
Material of imaged stack face can be swapped
Create Thermal Profile
Simulated Electronics System
Reference Data System
V&V of Thermal Camera Data
OTheRS System
IR Cameras
Thermal Ctrl

## Slide 4: CONOPS
Notes: thermal cameras will be mounted to the ceiling and floor of the bay, and image a single side of the rectangular electronics stack. Data will also be simulataneously taken from an array of thermistors mounted on the opposite side of the stack face. You can also see the camera has its own thermal managment system.
After the cameras captures an image, it is processed by stitching the images together, correcting for skew and extracting temperature infromation.
This information is then sent through a controller, which will send regulatory commands to LED’s as representative indicators of control ouput.
Data will also be sent to through a serial output, which will then be validated by comparing against the previously mentioned thermistor array.

## Slide 5: Functional Block Diagram

## Slide 6: Critical Project Elements
Critical Project Elements | Concerns/Updates Since CDR
Image Capture and Processing System | Image Processing is farther behind than expected. Image Stitching is now using hardcoded geometry
Test Bed Structure | Stack tray was redesigned, prototype in progress.
Thermal Control of Camera | Resistors being used as heaters PCB design under work
Full-Stack Regulation | Basic On/Off Control, integrated into IP software

## Slide 7: Project Schedule

## Slide 8: Image Processing and Manufacturing
Critical Path
2 camera interface with Raspberry Pi
Image Stitching
Identify Hotspots
Temp. Accuracy Calibration
TestBed Integration & Test
CAD Models
Tool Paths and
Tray Prototype
Machining and Assembly
PFR
MSR
TRR
SFR

## Slide 9: Other Project Elements
Critical Path
Procurement
PFR
MSR
TRR
SFR
Camera Thermal Regulation
Simulation Electronics
Reference Data System
Testing and Final Report

## Slide 10: Manufacturing Progress

## Slide 11: Mechanical

## Slide 12: Status of TestBed
In progress
Needed
Acquired
Camera Mounts
M
D
P
Standoffs
M
D
P
Removable stack face
M
D
P
Offset Plate
M
D
P
Bay Aluminum Angles
M
D
P
P
D
M
= procurement
= design
= manufacturing
Stack Trays
M
D
P
Stack Lid
M
D
P
Wall Clamps
M
D
P
Bay Walls
M
D
P

## Slide 13: Integration Plan
Test Bed Integration
Assemble Outer Bay
Test Camera Mount
E2E Testing
Complete System
Main Tasks
Integration Tasks
Final Tasks
Legend
Hardware Tasks
Unrelated Tasks
Manual Tasks
Testing Tasks
Assemble Stack
Test Part Fitment
Measure Parts
Manufacture Parts

## Slide 14: Electrical

## Slide 15: Wiring Diagram
Notes: This will have to be updated w/ the serial data comm hardware. Include RS232 to UART converter that connects to the Pi. 4 pins (GND is shared) used. Connects to the RasPi- Justin 2/1

## Slide 16: Full-Stack Regulation System

## Slide 17: Integration with project
Notes: This will have to be updated w/ the serial data comm hardware. Include RS232 to UART converter that connects to the Pi. 4 pins (GND is shared) used. Connects to the RasPi- Justin 2/1

## Slide 18: Tasks Resources Involved:
Receive PCBs
Assemble board
Control software
Receive components
Test Bed integration
Control software:
  Python
  Runs on embedded Raspberry Pi
Heater Driver PCB:
  Order from: JLCPCB (China), Digikey
  Design software used: KiCad
  Production + Shipping time: 2+ weeks
In progress
Needed
Complete
Component Selection
PCB Design

## Slide 19: Reference Data System

## Slide 20: Integration with project
Notes: This will have to be updated w/ the serial data comm hardware. Include RS232 to UART converter that connects to the Pi. 4 pins (GND is shared) used. Connects to the RasPi- Justin 2/1

## Slide 21: Tasks Resources Involved:
Component Selection
Assemble board
Write Monitor GUI software
Write ADC controller software
Monitor Software:
  Python 3.7
  Packages used: numpy, Tkinter, os, Matplotlib, pySerial, datetime, time
  Able to run on Linux, Windows
MCU Software:
  C++
  Able to run on Arduino Uno
ADC PCB:
  Order from: JLCPCB (China), Digikey
  Design software used: KiCad
  Production + Shipping time: 2+ weeks
In progress
Needed
Acquired
Integrate with GUI
Receive Components
Test Bed Integration
PCB Design
Receive PCBs

## Slide 22: Heater Driver Board

## Slide 23: Integration with project
Notes: This will have to be updated w/ the serial data comm hardware. Include RS232 to UART converter that connects to the Pi. 4 pins (GND is shared) used. Connects to the RasPi- Justin 2/1

## Slide 24: Tasks Resources Involved:
Embedded Software:
C++
Able to run on Arduino Uno
Other:
High density components may require reflow station in ITLL (TSSOP-16 and -28 packages)
Requires separate power supply for heater current
Component Selection
Assemble boards
Write Monitor GUI software
Write Heater driver software
In progress
Needed
Acquired
Integrate with GUI
Receive Components
Test Bed Integration
PCB Design
Receive PCBs
Driver PCB:
Order from: JLCPCB (China), Digikey
Design software used: KiCad
Production + Shipping time: 2+ weeks

## Slide 25: Image Processing Software

## Slide 26: Integration with project
Notes: This will have to be updated w/ the serial data comm hardware. Include RS232 to UART converter that connects to the Pi. 4 pins (GND is shared) used. Connects to the RasPi- Justin 2/1

## Slide 27: Software Task Progress

## Slide 28: Integration Plan
Test Bed Integration
Identify Hot Spots
Data Export
Embed Software
Software Automation
E2E Testing
Complete System
Main Tasks
Integration Tasks
Final Tasks
Legend
Software Tasks
Unrelated Tasks
Manual Tasks
Testing Tasks
Data Calibration
Data Extraction
Image Stitch
Image Capture
Unit Testing

## Slide 29: Budget

## Slide 30: Cost Breakdown As of MSR
IP Cost | $713.01
Ref Data Cost | $162.54
Sim Elec Cost | $228.00
Elec Cost | $237.90
Structural | $1,900.45
Grand Total | $3,241.90
Remaining | $1,758.10

## Slide 31: Future Cost Planning
Structural
  Lid ($124)
  Standoffs ($7)
  Removable Plates ($60 per plate)
  Offset Plate ($120)
Electronics
  PCB for the Heaters ($80 per PCB)
Coatings
  Remaining budget will be used to research coatings

## Slide 32: Questions?

## Slide 33: Back Up Slide Deck

## Slide 34: References
https://www.unitedaluminum.com/chemical-composition-and-properties-of-aluminum-alloys/
https://www.makeitfrom.com/compare/2014-T6-Aluminum/6061-T6-Aluminum
https://www.monolithicpower.com/pub/media/document/MP1584_r1.0.pdf
https://www.digikey.com/catalog/en/partgroup/lepton-breakout-board/55730?utm_adgroup=Programmers%20Dev&slid=&gclid=EAIaIQobChMIkf6j54WE3wIVFx6tBh1j3gDuEAAYAiAAEgIv9PD_BwE
https://www.midstateinstruments.com/iriss-small-shaped-high-emissivity-target-labels-4-x-500/
https://www.instructables.com/id/Read-and-write-from-serial-port-with-Raspberry-Pi/

## Slide 35: Baseline Design

## Slide 36: Grounding The Testbed
The Test bed will be grounded through the utilization of solderless crimp terminals.
These will connect to the aluminum surface and then to a grounding terminal.
Figure: Solderless crimp Terminal

## Slide 37: Mechanical Structure Status

## Slide 38: Design of Testbed

## Slide 39: Tray Design

## Slide 40: Tolerances
± 0.01 inch = 0.254 mm
16.538° ± 3° (vertical angle, camera mount)
52° ± 7° (horizontal angle, camera mount)
Most important components to minimize tolerance:
Stack walls - want to keep heat isolated to inside the stack
Bay walls - want to keep system isolated, don’t want outside light entering testbed
Camera mount - want to be able to image entire side of stack

## Slide 41: Thermal Model Status

## Slide 42: Thermal Model
Wiring and Realistic Heater Performance

## Slide 43: Software Development

## Slide 44: Current Challenges - Image Stitching
Image stitching will resolve two thermal images into one.
The current Stitch API does not create a stitch for small images (160x120)
Custom solution script currently in development taking advantage of pre-determined coordinates
Testing will resume Feb. 7th
Test 4: 160X120 pixels
Test Results:
Significant Matches Found? - Success
Comprehensive Stitch - Fail
2
1
Not enough matches found!
Fig. 1,2: Input Thermal Images
Fig. 3: Results
Notes: Main change since CDR is depth of testing. The current software does not provide a stitch for images so small. Solution script is currently in development.
Notes: Based on current research, the current industry-preferred method for stitching does not perform well with low-resolution images. The image processing for this project is a case-study on if this can be done. This software module is top priority. - Justin

## Slide 45: Current Challenges - Serial Data Comm.
Serial data communication protocol will be RS232, as specified by the customer.
Code has been written, preliminary testing
Currently, the RasPi can write to the RS232 to UART converter but not read
Testing will resume Feb. 5th
Fig. 1: RS232 to UART converter
Testing Results:
RasPi Code Write - Success
RasPi Code Read - Fail
Send serial data to host - Fail
Test 1: Serial Communication
Potential Hardware Issue
Notes: As defined by our customer, system will need to communicate via serial comm protocal RS232. In the current test setup, RPi sends data to the laptop. Temperature data is sent along these lines of communication.

## Slide 46: Software Development Timeline
Image Sensing:
Find workable Image Capture Module
Configure FLIR Lepton w/ RasPi
Useful images test (initial testbed)
Thermal Image Capture
Enable radiometry feature via Lepton SDK
Radiometric image testing
Temperature data post-processing
Improve dynamic range (8bits -> 14 bits per channel)
Verify temperature data
Configure 2x FLIR Lepton w/ RasPi
Test image capture w/ both cameras
Infant Stages
In progress
Complete
Since CDR

## Slide 47: Software Development Timeline
Image Stitching:
Find workable Image Stitching Module
Research stitching methods
Research Stitching API (ORB Stitching)
Timing analysis for OpenCV stitching methods
Testing stitching module
Test stitching module with high-resolution images
Test stitching module with high-resolution thermal image
Test stitching module with low-resolution thermal image
Test stitching module with low-resolution low-quality thermal image
Researching additional image stitching methods
Brainstorming custom software options
Locate keypoint matches between the two images (hard-code)
Develop comprehensive stitch, preserving data
Infant Stages
In progress
Complete
Since CDR

## Slide 48: Other Stitching Tests
Stitch test with FLIR 3.5
Result: Failure, Not enough accurate matches were found to complete the stitch
Captured Image
Image A to Stitch
Raw Match Data

## Slide 49: Rs232 to UART Converter

## Slide 50: IP Hardware Interfacing
RS232 to UART converter
FLIR Lepton Cameras
Notes: Current use of pins on the RasPi. External hardware involved: RS232 to UART converter and 2 FLIR Lepton cameras.

## Slide 51: Full Stack Regulation System

## Slide 52: Integration Plan

## Slide 53: Full Stack Regulation System Schematic

## Slide 54: Heater Driver System

## Slide 55: Heater Driver Schematic

## Slide 56: Heater Driver PCB

## Slide 57: Reference Data System

## Slide 58: Integration Plan

## Slide 59: Monitor GUI

## Slide 60: Reference Data System Schematic

## Slide 61: Reference Data System PCB

## Slide 62: Coatings

## Slide 63: Preliminary Coatings Testing
4 types of coating families selected for testing on prototype test bed
  Bare Aluminum
    Baseline case
  Sticky Notes
    Replicate Customer case
  Tape
    Increase conduction from sticky note test
  Sanded Face
    Find dependency on surface roughness
Metrics established to score coatings
  Are material properties changing?
    Temperature of reference data system compared with bare Aluminum test
  Is accuracy increased or reflection mitigated?
    Temperature of thermal imaging device compared with bare Aluminum test
  Is the thermal behavior captured by the thermal imaging device?
    Temperature of reference data system compared with thermal imaging device

## Slide 64: Continued Coatings Testing
Testing on the final testbed will have dependencies on findings from preliminary testing
Testing will be completed on the final test bed design
Coatings to be tested
  Slide in sheet of Aluminum 6061
    Quantify effect of thermal contact resistance
  Material variation
    Vary material attached to face being imaged
  Surface coatings
    Time and budget constraints
    Intention to test coatings with similar space grade variants
      Aids the customer for their application

## Slide 65: Budget

## Slide 66
Purchases Made Up Until MSR |  |  |  |  |  |  |  |  | 
Sub-System | Part | Unit Price | Qty | Total | Sub-System | Part | Unit Price | Qty | Total
IP/Camera | FLIR Lepton 3.5 | $301.01 | 2 | $610.02 | Ref Data | Sparkfun RedBoard | $19.95 | 1 | $24.95
IP/Camera | Lepton 3.5 Breakout | $0.00 | 2 | $0.00 | Ref Data | Resistors - CRGCQ0402F18K | $0.10 | 80 | $8.00
IP/Camera | High Emmisivity Stickers | $53.00 | 1 | $62.99 | Ref Data | Custom PCB | $10.00 | 3 | $30.00
IP/Camera | Raspberry Pi 3b | $40.00 | 1 | $40.00 | Sim Elec | Custom PCB | $8.00 | 10 | $85.00
Structural | Aluminum 6061-T6 Plates .04"x2'x4' in (Bay) | $59.90 | 10 | $639.00 | Sim Elec | Power Resistor - 71-RS01025R00FE73 | $1.19 | 100 | $119.00
Structural | Toggle Clamps | $19.99 | 4 | $87.96 | Sim Elec | Power Driver Board | $8.00 | 3 | $24.00
Structural | Aluminum 6061-T6 Plates (1/16") - 25.5"x24" | $69.50 | 3 | $248.50 | Sim Elec | D-Type Connectors | $0.00 | 0 | $0.00
Structural | Aluminum 6061-T6 Plates (1/16")13.5"x25" | $69.50 | 3 | $208.50 | Electronics | Buck Converter | $6.99 | 2 | $13.98
Structural | Aluminum 6061-T6 Plates (1/16") 24"x13.5" | $49.50 | 3 | $148.50 | Electronics | Wiring - 12 Gauge | $15.95 | 2 | $36.90
Structural | Foam Insulation | $32.60 | 1 | $32.60 | Electronics | D-type Connector | $1.57 | 0 | $0.00
Structural | AL 6061 Plate | $59.90 | 2 | $119.80 | Electronics | AC Adapter | $19.99 | 1 | $19.99
Structural | AL 6061 Sheet Metal | $101.75 | 3 | $305.25 | Electronics | USB for Arduino | $34.99 | 1 | $34.99
Structural | M2 Tap Starting | $16.53 | 2 | $33.06 | Electronics | MOSFET 60V | $0.71 | 10 | $15.05
Structural | M2 Tap Closed | $16.53 | 2 | $33.06 | Electronics | IC LED DRIVER | $2.33 | 3 | $6.99
Structural | 18-8 Stainless Steel Slotted Flat Head Screws | $7.79 | 1 | $7.79 | Electronics | MOSFET 55V | $1.08 | 3 | $3.24
Structural | Paper Tape | $9.89 | 1 | $9.89 | Electronics | CAP ALUM 47UF 20% 63V RADIAL | $0.33 | 4 | $1.32
Structural | Threaded Rod 40x6 H44815E | $1.08 | 10 | $10.80 | Electronics | TE Connectivity Amp Connectors | $1.04 | 3 | $3.12
Structural | Nut Hex H140009E | $0.08 | 20 | $1.62 | Electronics | CONN HEADER R/A | $3.70 | 6 | $22.20
Structural | MS Metric Phil Pan M2X12 H4307E | $0.30 | 32 | $9.50 | Electronics | 25W Chassis Resistors | $3.08 | 2 | $6.16
Structural | MS Metric Phil Pan M2X8 H4306E | $0.24 | 19 | $4.62 | Electronics | Thermocouple BreakOuts | $12.76 | 2 | $25.52
Ref Data | Thermistors - Vishay NTCLE413 | $1.39 | 45 | $70.55 | Electronics | Power Resistor Kit | $4.76 | 1 | $4.76
Ref Data | Screw Terminals | $0.80 | 10 | $10.00 | Electronics | MOSFET Transistors | $2.03 | 10 | $20.30
Ref Data | ADC - ADC128D818 | $4.68 | 3 | $19.04 | Electronics | Arduino Uno | $23.38 | 1 | $23.38