## Slide 1: WHiMPS
Windmill Hindrance and Maneuverable Propulsion System
Team:
Alec Bosshart
Isobel Griffin
Julia Kincaid
Andrew Meikle
Declan Murray
Alexandra Paquin
Andrew Robins
Liam Sheffer
Jon Weidner
Zoe Witte
Lucas Zardini
Nick Zellmann
Test Readiness Review
Advisor: Dr. Donna Gerren
Customer: Air Force Research Laboratory
POC: 1LT Riley Huff
Notes: Presenter:

## Slide 2: Overview
Overview
Manufacturing Status
Testing Status
Schedule
Electronics/Software Status
Budget
Notes: Presenter:

## Slide 3: Problem Statement
Implement thrust vectoring capabilities to the JetCat P100-RX Engine
Prevent windmilling of the fan blades while under flight conditions of Mach 0.8 flow at 20k feet
Motivation
The United States Air Force Research Lab (AFRL) would like to investigate implementing thrust vectoring capabilities and windmill prevention into the JetCat P100-RX Engine
The ideal solution would be simple, with a single mechanism and controls to accomplish both tasks
Notes: Presenter:

## Slide 4: Project Purpose Visualization
Notes: Presenter:

## Slide 5: Concept of Operations
Notes: Presenter:

## Slide 6: Levels of Success
Notes: Presenter:

## Slide 7
Notes: Presenter:

## Slide 8: Baseline Design - WPM
ICUP
Solenoid Housing
Fairing
Fore Retention Ring
Solenoid Pins
Notes: Presenter:

## Slide 9: Baseline Design - TVM
Paddle
Linkage Rod
Nozzle Sheath
Actuator Ring
Linear Actuator
Linear Potentiometer
Linear Potentiometer Arm
Actuator Pod
Notes: Presenter:

## Slide 10: Changes Since MSR
Redesign to ICUP component
  Due to risk of collision during ejection, along with spacing issues on the engine we have decided to redesign the ICUP
  New design will consist of 4 connected PCBs that will go along engine body
    This design reduces risk of collision, and decreases form factor of engine
    Redesign does not require increase in board complexity
Redesign to fore retention ring
  Response to very limited space on the engine
    P100-RX is the smallest engine ever used by CU APOP team
  Will have to interface with ICUP component
Redesign of actuator housing
  Switch from ABS plastic to Aluminum 6061
  Response to PAB concerns with the 3D printed housing that holds the actuators
Notes: Presenter:

## Slide 11: Critical Project Elements
Designation | CPE | Critical Characteristics
CPE-1.2 | Windmill Prevention Mechanism (WPM) and Thrust Vectoring Mechanism (TVM) | Thermodynamic and structural analysis require assumptions of materials and operating conditions. Further analysis shall characterize and define risks.
CPE-3.1 | Main Control Board (MCB) | During testing and product development, this will verify safe engine operation and monitor WPM/TVM.
CPE-3.2 | Integrated Communication Unit Panel (ICUP) | Minimizes amount of wires to reduce risk of human error and increases processing speed.
CPE-3.3 | Software | Controls the incorporated mechanisms over the entire operational envelope.
Notes: Presenter:

## Slide 12: Schedule
Overview
Manufacturing Status
Testing Status
Schedule
Electronics/Software Status
Budget
Notes: Presenter:

## Slide 13: Schedule Overview - Manufacture/Testing
WPM manufacture and test
Acquisitions
Manufacturing
Test prep
Testing
TVM manufacture and test
Deliverables
WPM manufacture and test
Notes: Presenter:

## Slide 14: WPM Manufacture and Test Schedule
Acquisitions
Manufacturing
Test prep
Testing
Notes: Presenter:

## Slide 15: TVM Manufacture and Test Schedule
Acquisitions
Manufacturing
Test prep
Testing
Notes: Presenter:

## Slide 16: Electronics and Software Schedule
PCB Rev. A
PCB Rev. B
PCB Rev. C
Labview Dev.
MCB Dev.
Notes: Presenter:

## Slide 17: Manufacturing Status
Overview
Manufacturing Status
Testing Status
Schedule
Electronics/Software Status
Budget
Notes: Presenter:

## Slide 18: WPM Manufacturing Overview
Fairing 3D print using carbon fiber reinforced Onyx
Solenoids from Adafruit
Windmill prevention APOP test replica
Ejection springs from McMaster-Carr
Fore retention ring 3D print → 1 week, approximately 2 days printing
Windmill prevention high speed flow test → 1 week acquisitions
Aluminum 6061 ejection pins → 6 hours lathe
Completed
In Progress
Not Started
Notes: Presenter:
Only really talk about the ones that aren’t completed, breeze over completed ones

## Slide 19: TVM Manufacturing Overview
Stock engine test with dummy paddles
3D printed actuator nut attachments
Sheath hinges
Clevis pins from McMaster-Carr
Thrust vectoring test stand → 1 week drilling and assembly
Steel linkage rods → 6 hours milling
3D printed potentiometer arms → 4 hours print
Steel paddles → outsourced, 1 week expected
Steel nozzle sheath → successful prototypes, 1 week
Actuator ring → 2 weeks
Completed
In Progress
Not Started
Notes: Presenter:
Only really talk about the ones that aren’t completed, breeze over completed ones

## Slide 20: Electronics & Software Test Status
Overview
Manufacturing Status
Testing Status
Schedule
Electronics/Software Status
Budget
Notes: Presenter:

## Slide 21: Electronics Overview
Main Control Board (MCB)
Provides WHiMPS’ data processing and power distribution
Integrated Communication Unit Panel (ICUP)
Extends actuators and potentiometers’ data and power lines from the MCB to the engine
Linear Potentiometer Breakout Board (LPBB)
Converts potentiometer analog output to a digital signal (I2C)
ICUP
MCB
LPBB
Rev. A
Notes: Presenter:

## Slide 22: Electronics Testing
Switch functionality
Voltage converter (5V)
Power protection circuit
GPIO/LED circuit
Power MOSFET circuit
Raspberry Pi functionality
I2C functionality
Solenoid circuit
Actuator/motor driver circuit
Linear potentiometer circuit
Harness continuity check
Temperature sensor circuit
Successful
Successful After Changes
Unsuccessful
MCB
ICUP
LPBB
All
Notes: Presenter:

## Slide 23: Upcoming Electronic Tests
Temperature sensor addresses
  Done by: 3/6/2020
Actuator/motor driver circuit
  Done by: 3/6/2020
Load cell/amplifier circuit
  Done by: 3/13/2020
Revision B MCB functionality
  Done by: 3/13/2020
Revision B ICUP functionality
  Done by: 3/13/2020
Revision B LPBB functionality
  Done by: 3/13/2020
Revision A PCBs
Notes: Presenter:

## Slide 24: MCB Revision B
Changes from Revision A to B:
Took out MCB <-> ECM connector
Fixed the temperature sensor circuit
Added load cells connectors and amplifiers (2x)
Added more indicator LEDs
Added MOSFETs for all motor drivers/actuators
Took out software control (MOSFET) for Ammeter
Notes: Presenter:

## Slide 25: ICUP Revision B
Changes from Revision A to B:
Changed outline from a ring to a 4 panel “bracelet” design
  Each panel is connected together through SAMTEC locking connector assemblies
Motor drivers were replaced with the correct stepper motor driver
Fixed solenoid circuit
Using a surface mount rail system with one screw hole instead of 4 screw holes
1
MCB <-> ICUP
Actuator #1
Motor Driver #1
LPBB #1
2
Solenoid #1
Actuator #2
Motor Driver #2
LPBB #2
3
Actuator #3
Motor Driver #3
LPBB #3
4
Solenoid #2
Actuator #4
Motor Driver #4
LPBB #4
Notes: Presenter:

## Slide 26: LPBB Revision B
Changes from Revision A to B:
Changed to an ADC with multiple address for I2C
  Tie AD0 and AD1 resistors to either HIGH or LOW to get 4 address combinations
  18 bit ADC
Notes: Presenter:

## Slide 27
Notes: Presenter:
Notes: Everything is pretty much done - waiting on having all the hardware integrated together to test Success Criteria 2-3, also need to finish the the Hardware WPM Class (almost done)

## Slide 28
Notes: Presenter:
Most of the work left relies on getting the actuators to work (waiting on hardware), calibrating the potentiometers (waiting on hardware), testing feedback loop with potentiometers and actuators, also need to do the Load cells and finish the software simulated implementation of the thrust vectoring mechanism

## Slide 29
Notes: Presenter:
For MCB, need to test my calibration code on the hardware (waiting for batteries to be integrated to test this)
For Engine, need to write and test the interface for aquiring data from the ECU as well as test the RS232 driver that is already written with the ECU
For LabView, need to test the RS232 driver that is already written with Labview
For success criteria 4: once previous success criterias have been met just need to run the code with this build configuration and test to make sure everything is working well together
For success criteria 5: need success criteria 4 to be complete and the engine related software to be complete to test to make sure everything is working well together

## Slide 30: System Testing Status
Overview
Manufacturing Status
Testing Status
Schedule
Electronics/Software Status
Budget
Notes: Presenter:

## Slide 31: Engine Testing Progression
Stock Run, 2/24 ✅
Understand engine operation
Stock w/ Dummy Paddle, 2/26 ✅
Helps satisfy safe operation and stock engine functionality requirements
Vibration and Thrust Baseline, 3/12*
Characterize vibration and thrust
Static TVM Test, 4/6*
Validate ability to vector thrust using paddles preset in deflected position
Dynamic TVM Test, 4/13*
Verify ability to vector thrust by commanding paddle movement during engine operation
*tentative
APOP Replica Test, 3/3*
Verify fairing prevents airflow under pressure differential
SABRE Static WPM Test, 3/16*
Validate fairing function at Mach 0.8
SABRE Dynamic WPM test, 3/19*
Verification of ability to eject fairing at Mach 0.8
Integration Tests, 4/15*
TVM Testing
WMP Testing
Notes: Presenter:

## Slide 32: Stock Engine and Dummy Paddle Test
Verified that JetCat P100-Rx is functioning and operating correctly
Validated thermal model before implementation of hardware
Verified engine did not turn off when flow was deflected using dummy paddles
Equipment
  Engine, associated tanks and lines
  Test stand
  Paddles and attachment mechanisms
  Fuel and oil, in tank
  Thermocouples
  GSU and battery
Facilities
  CU Aerospace Test Cell
Notes: Presenter:

## Slide 33: Thermocouple Data
Cooldown
Idle
Max RPM
Max RPM
Idle
Cooldown
Aluminum Max Temp: 572°C
304 SS Max Temp: 925°C
Notes: Presenter:
Note that 304 steel has a melting point of 1400C, but can be used in continuous manner up to 925C

## Slide 34: Thermocouple Data
Note: We did have a slight separation of the thermocouple and the paddle around t=90s due to a tape failure, resulting in the slow degradation of the measured temperature
Steel Max Temp: 700°C
Carbon Fiber Reinforced Onyx Max Temp: 145°C
Notes: Model predicted 400C for back of paddle, so we’re doing fine in that regard

## Slide 35: Risk Reduction and Expectations
Risk Reduction
  Ensures that operation of the engine is attainable
  Demonstrates that flow deflection will not interfere with engine operability
  Obtain better understanding on power limitations (run-time) to safely operate engine
  Vibrational, thermal, and thrust data mitigates risk of engine components detaching during operation
Expected Results
  Engine operation is successful and repeatable
  Temperatures will be at or below thermal requirements
  Dummy paddles will not interfere with engine operability
Model Validation
  Thermal model demonstrating paddles can withstand heat
Dummy paddles
Notes: Presenter:

## Slide 36: Static and Dynamic Thrust Vectoring Tests
Purpose: prove that paddles vector the thrust without altering the engine’s operation
  Verifies zero impedance at 0° and two-axis ±10° capabilities
Equipment
  Engine, associated tanks and lines
  Test stand w/ second axis
  Paddles and attachment mechanisms
  Fuel and oil, in tank
  Thermocouples
  GSU and battery
Facilities
  CU Aerospace Test Cell
MOST CRUCIAL TVM TEST
Notes: Presenter:

## Slide 37: Risk Reduction and Expectations
Risk Reduction
  Progressive testing will reduce mechanical risks
    Mechanical risks include fracture of components and melting of ABS components
  Paddles will be pre-deflected so no mechanical motion is required during first full TVM test
Expected Results
  Thrust will be vectored at ±10° in two body axes
  Zero impedance of thrust at 0° deflection
Model Validation
  Thrust vectoring CFD model showing necessary paddle angles for desired deflection
  Paddle thermal and structural FEA models
𝝰
Pp
Ps
Nozzle
Pr
Notes: Presenter:

## Slide 38: Thrust Vectoring Test Safety Measures
Safety Concerns:
  Fuel fire
  Engine breaks and throws a fan blade
Safety Measures
  All tests performed in CU engine test cell
  Matt Rhode present for all tests
  Safety officer is only member in test cell once battery is plugged in
  Sentries posted outside of test cell to stop passersby from entering danger zone
Notes: Presenter:

## Slide 39: WPM APOP Replica, Test #1
Used to simulate Mach 0.8 airflow at 20,000 ft via a 3.5 psi pressure differential
Engine not operating
Equipment
  PVC pipe with attached pressure gauge and foam insert
  Air compressor
  Air lines and connectors
  Pressure regulator
  3D printed fairing
  Test mount
Facilities
  CU Aerospace Test Cell
MOST CRUCIAL WPM TEST
Notes: Presenter:

## Slide 40: Risk Reduction and Expectations
Risk Reduction
  Provides redundancy for APOP demonstration to ensure test will be successful
  Provides necessary information to determine if further mitigation is necessary, such as adding in an O-Ring to prevent flow leakage
Expected Results
  Fairing will withstand the 3.5 psi pressure differential
  The engine will experience 0 RPM of the fan blades
Model Validation
  FEA structural model of fairing displacement under 3.5 psi pressure differential
Air Force
Test Diagram
Notes: Presenter:

## Slide 41: WPM High Speed Flow (SABRE), Test #2
Provides Mach 0.8 airflow for several seconds to test fairing structural integrity and seal
Equipment
  2 pressure regulators
  2 pressure gauges
  Outlet nozzle (3D printed)
  SABRE tanks and system
  Engine test mount
  3D printed fairing mounted on engine
  Electronics and software
Facilities
  CU Aerospace Test Cell
6ft
Notes: Presenter:

## Slide 42: Risk Reduction and Expectations
Risk Reduction
  Ensures ejection mechanism will not damage external components
  Shows ICUP redesign is sufficient to avoid damage during ejection
Expected Results
  Fairing will withstand Mach 0.8 flow
  The engine will experience 0 RPM of the fan blades
Model Validation
  FEA structural model of fairing displacement under high speed flow
  CFD model confirming the turbulent wake aft of the engine re-entering the nozzle should not be a concern
Notes: Presenter:

## Slide 43: Windmill Prevention Test Safety Measures
Safety Concerns
  Over-pressurization of the APOP replica PVC Tube
  Failure of SABRE tank
  High speed air harming passersby of test cell
Safety Measures
  Matt Rhode present for all tests
  Pressure gauge on PVC tube
    Safety officer radios to valve operator to shut off if differential pressure exceeds 5 psi
  Remotely pulling SABRE tank lever
  Same sentry/perimeter procedure as engine tests
  Complete depressurization of SABRE tanks before any transportation of tanks
Notes: Presenter:

## Slide 44: Budget
Overview
Manufacturing Status
Testing Status
Schedule
Electronics/Software Status
Budget
Notes: Presenter:

## Slide 45: Procurement Status Major Items
Procured
Pending
Planned
JetCat P100-RX engine
Clevis pins
Solenoids
Aluminum 6061 plates
Actuators
Raspberry Pi
Steel Linear Shafting
Stainless Steel 17-4PH
Fairing
Load Cells
WPM APOP test materials
Temperature sensors
Aluminum 6061 stock
Test stand modification rails
Misc electronic population materials
LPBB Rev B
MCB Rev B
ICUP Rev B
Paddles
Paddle Necks
Ejection Springs
Fore Retention Ring Print
WPM SABRE test materials
Notes: Presenter:
These are the things we are procuring outside of CU (i.e. not manufacturing ourselves)
We can breeze over this slide, just wanted it to appease the rubric

## Slide 46: Financial Budget Status
Spent 58% of funds
After running engine multiple times we have decided to abandon the idea of saving for an additional engine.
We will use funds to guarantee thrust vectoring and windmill prevention success as well as allow for all tests possible.
Electrical / Software | $ 459.95
Thrust Vectoring | $ 1101.58
Windmill Prevention | $ 103.78
General / Tests | $ 1153.05
Notes: Presenter:

## Slide 47: Questions?

## Slide 48: Backup

## Slide 49: Fairing Ejection Animation

## Slide 50: TVM Animation

## Slide 51: Fairing Displacement
Dr. Maute identified component displacement as most important quality
FEA was conducted for each component separately
  Component Displacements:
    Left Side Fairing: 1.123e-7 mm
    Right Side Fairing: 4.03e-3 mm
These results are with each component acting independently
  Mounting the two pieces together will provide additional structural support
Notes: Zoe

## Slide 52: Design Validation
CFD conducted simulating Mach 0.8 at 20,000 ft
Professor John Mah confirmed the turbulent wake aft of the engine re-entering the nozzle should not be a concern
Notes: Zoe

## Slide 53: Thrust Vectoring CFD Results
θ = 17°
θ = 11°
A = 1250mm2
A = 850mm2
Paddles are at 20°
Paddles are at 20°
Notes: Jon

## Slide 54: Thrust Vectoring CFD Results Cont.
Probable causes of difference in results
  CFD can calculate momentum at each point more accurately
  Model does not account for flow entrainment
Using smaller paddle area (850mm2)
  More confidence in CFD
Notes: Jon

## Slide 55: Sheath Structural Analysis
Material modeled as Aluminum 2024
Yield strength - 325 MPa
Max total axial force - 100N+
Failure mode is bending point
Load would be distributed with actuator linkage.
Notes: Jon

## Slide 56: Actuator Housing Structural Analysis
ABS Plastic 3D printed structure
Assumes front lip is fixed; load is dynamic pressure on rear cross sectional area (overestimate).
ABS Strength ~ 40 MPa
Max von Mises stress = 643 kPa
FOS = 62
Glass transition temperature = 98°C
Engine base doesn’t get significantly hotter than ambient conditions in previous tests.
Notes: Jon
Strength from Simplify3D.com

## Slide 57: Paddle Structural Analysis
Service Temp of 700K > 668K max temp from thermal model
From CFD, each paddle experiences 7.31N normal to plane at center of paddle
  Similar to base principle estimate
Assumes pins fixed; 8N normal load to paddle
Max von Mises stress of 96 MPa < 620 MPa yield strength (FS = 6.5)
Stainless Steel 0.04” thick sheets cut then rolled into shape.
Notes: Jon

## Slide 58: Vibrational Analysis
Engine frequency range between idle and max thrust state (50 N to 100 N)
  733.3 Hz ≤ f ≤ 2566.7 Hz
Two main points of concern are the paddle and rod connection between actuator screw and paddle
  Actuator and screw will absorb some of the engine excitation (damper)
Material is modeled as T-600 Steel with a modulus of elasticity of ~200 GPa
  Paddle: f = 18.28 Hz
  Rod: f = 329 Hz
Actuator, screw, nozzle sheath, and plastic housing will act as dampers to dissipate energy, further reducing risk of vibrational failure
Notes: Because the largest natural frequency is 329 Hz, which is far less than engine idle state, we can accept the components as good to go.
Jon

## Slide 59: List of Necessary Materials
Windmill Prevention Mechanism (acquire)
  PVC and PVC cap
  Pressure regulator
  Pressure gauge
  Air line (50ft)
  NPT connectors (¼”)
Thrust Vectoring Mechanism (acquire)
  Load cell/load cell amplifier
  Pillow blocks
  Steel shafts
  Aluminum plates
  Compression springs
Electronics/Software (acquire)
  Connectors
  Motor drivers
  Actuators
Windmill Prevention Mechanism (manufacture)
  Outlet 3D-printed nozzle (SABRE)
Thrust Vectoring Mechanism (manufacture)
  Paddles/linkages
Electronics/Software (manufacture)
  MCB
  LPBB (x4)
  ICUP
  MCB housing

## Slide 60: Stock engine testing (preheating)

## Slide 61: Stock engine testing (visible exhaust)

## Slide 62: Risk Reduction
ICUP design is being modified to resemble a bracelet, rather than a donut
  Reduces risk of ICUP breaking under load of the Mach 0.8 air and from ejection of the fairing hitting the ICUP
  Ensures that fairing ejection does not interfere with the electronic components onboard the engine
New design
Notes: Presenter:

## Slide 63: WPM Test #1 plan

## Slide 64: Stock Engine and Dummy Paddle Test