## HOME
SHRP2 Risk Management Template (Montecarlo Approach)
Home
PROJECT INFORMATION
AGENCY : | Federal Highway Administration |  |  | FACILITATOR : | Carlos F Figueroa
LOCATION : | QDOT District 1 |  |  | PROJECT MANAGER : | Luis Millan
PROJECT NAME : | QDOT Example |  |  | DATE : | 2015-08-31
PROJECT DESCRIPTION : | QDOT Example R09 v2 Guidebook |  |  | VERSION : | 2
RISK MANAGEMENT TEMPLATE STEPS
Enter base project information (schedule, cost, etc.).
Create list of potential risks.
Enter severity information for each risk to assess risk impact.
Evaluate risks and uncertainties
Step 01 - Project Structuring
Step 02 - Risk Identification
Step 03 - Risk Assessment
Step 04 - Dashboard
Project Reset

## 1-Hidden (hidden)
Design-Bid-Build
Project Start Date |  | 2014-02-04
Target Date for Start of Operations |  | 2014-05-05
Schedule Value
| Months/Date | Early Start | Early Finish | Late Start | Late Finish | Float | 3
Planning | 0 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 0 | 2
Scoping | 0 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 0 | 42522
Design Funding Date | 2009-12-01 |  | 2009-12-01 |  | 2009-12-01 | 0 | 6
Prelim Design/Environmental Process | 12 | 2009-12-01 | 2010-11-30 19:12 | 2009-12-01 | 2010-11-30 19:12 | 0 | 6
Environmental Permits | 6 | 2010-11-30 19:12 | 2011-06-01 04:48 | 2011-06-01 04:48 | 2011-11-30 14:24 | 6 | 42736
ROW/Util/RR Funding Date | 2009-12-01 |  | 2009-12-01 | -1179621.6 | 2011-11-30 14:24 | 24 | 5
ROW/Util/RR | 12 | 2010-11-30 19:12 | 2011-11-30 14:24 | 2010-11-30 19:12 | 2011-11-30 14:24 | 0 | 4
Final Design | 6 | 2010-11-30 19:12 | 2011-06-01 04:48 | 2011-06-01 04:48 | 2011-11-30 14:24 | 6 | 43101
Construction Funding Date | 2009-12-01 |  | 2009-12-01 | -1179621.6 | 2011-11-30 14:24 | 24 | 8
Procurement | 6 | 2011-11-30 14:24 | 2012-05-31 | 2011-11-30 14:24 | 2012-05-31 | 0 | 23
Construction | 16 | 2012-05-31 | 2013-09-29 09:36 | 2012-05-31 | 2013-09-29 09:36 | 0
Operations & Maintenance | 600 | 2013-09-29 09:36 | 2063-09-07 09:36 | 2013-09-29 09:36 | 2063-09-07 09:36
Replacement | 0 | 2063-09-07 09:36 | 2063-09-07 09:36 | 2063-09-07 09:36 | 2063-09-07 09:36
Design-Build
Project Start Date
Target Date for Start of Operations
Schedule Value
| Months/Date | Early Start | Early Finish | Late Start | Late Finish | Float
Planning | 0 | 2009-12-01 | 2009-12-01 | 2009-11-30 22:22 | 2009-11-30 22:22 | -0.00225 | 3
Scoping | 0 | 2009-12-01 | 2009-12-01 | 2009-11-30 22:22 | 2009-11-30 22:22 | -0.00225 | 2
Design Funding Date | 2009-12-01 |  | 2009-12-01 |  | 2009-11-30 22:22 | -0.00225 | 43101
Prelim Design/Environmental Process | 12 | 2009-12-01 | 2010-11-30 19:12 | 2009-11-30 22:22 | 2010-11-30 17:34 | -0.00225 | 6
Environmental Permits | 6 | 2010-11-30 19:12 | 2011-06-01 04:48 | 2010-11-30 19:12 | 2011-06-01 04:48 | 0 | 6
ROW/Util/RR Funding Date | 2009-12-01 |  | 2009-12-01 |  | 2011-11-30 14:24 | 24 | 43282
ROW/Util/RR | 12.0023 | 2010-11-30 19:12 | 2011-11-30 14:24 | 2010-11-30 17:34 | 2011-11-30 14:24 | 0 | 1900-01-02
Construction Funding Date | 2009-12-01 |  | 2009-12-01 |  | 2010-11-30 19:12 | 12 | 43831
Procurement | 6 | 2010-11-30 19:12 | 2011-06-01 04:48 | 2010-11-30 19:12 | 2011-06-01 04:48 | 0 | 8
Final Design | 6 | 2011-06-01 04:48 | 2011-11-30 14:24 | 2011-06-01 04:48 | 2012-05-05 19:48 | 5.1719 | 10
Construction | 16 | 2011-07-01 14:24 | 2012-11-04 05:24 | 2011-07-06 19:48 | 2012-11-04 05:24 | 0 | 18
Operations & Maintenance | 600 | 2012-10-30 | 2062-10-08 | 2012-10-30 | 2062-10-08
Replacement | 0 | 2062-10-08 | 2062-10-08 | 2062-10-08 | 2062-10-08
Risk Brainstorm Help Table
Planning | PL
Scoping | SC
Design Funding | F1
Prelim Design/Environmental Process | PD
Environmental Permits | EP
ROW/Util/RR Funding | F2
ROW/Util/RR | RR
Final Design | FD
Construction Funding | F3
Procurement | PR
Construction | CR
Operations & Maintenance | OM
Replacement | RP
Phases - Cost & Disruption
Planning
Scoping
Prelim Design/Environmental Process
Environmental Permits
ROW/Util/RR |  | Threat
Final Design
Procurement
Construction
Operations & Maintenance
Replacement
Phases - Duration
Planning
Scoping
Design Funding
Prelim Design/Environmental Process
Environmental Permits
ROW/Util/RR Funding
ROW/Util/RR
Final Design
Construction Funding
Procurement
Construction
Risk Type List
Threat
Opportunity
Input for copying charts
Copy Thrt_Unmit? | TRUE
Copy Opp_Unmit? | TRUE
Copy Thrt_Mit? | TRUE
Copy Opp_Mit? | TRUE
Start Row - Risk Mitigation | 67
Formulas:
Early Finish = IF(OR([Early Start]="",[Months/Date]=""),"",[Early Start]+([Months/Date]*30.4))
Early Finish = IF([Months/Date] ="", "",[Months/Date])
Late Start = IF(OR([Late Finish]="",[Months/Date]=""),"",[Late Finish]-([Months/Date]*30.4))
Late Finish = IF([Late Start, row below] = "", "",[Late Start, row below])
Late Finish = IF(OR([Late Start, row below]="",E13="",E14=""),"",MIN([Late Start, row below],E13,E14))
Early Start = IF([Early Finish, row above]="","",[Early Finish, row above])
Early Start = IF(OR([Early Finish, row above]="",D8=""),"",MAX([Early Finish, row above],D8))

## 1 - Project Structuring
SHRP2 Risk Management Template (Montecarlo Approach)
Step 01 - Project Structuring
ANALYSIS - Select the "Analysis" button on the left to enter values in the "Analysis" portion of this sheet
| Project Delivery Method | Design-Build |  | Include Operations, Maintenance, & Replacement? |  |  |  | Yes
| Selected Perfomance Measures | Schedule
Cost
Disruption
SCHEDULE
| Project Start Date |  | 2009-12-01
| Target Date for Start of Operations | (Open to Traffic Date) | 2012-10-30
| Schedule Value ($M/month) |  | 0.1
| Project Phase | Months/Date | Early Start | Early Finish | Late Start | Late Finish | Float (months)
| Planning | 0 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 0
| Scoping | 0 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 0
| Design Funding Date | 2009-12-01 |  | 2009-12-01 |  | 2009-12-01 | 0
| Prelim Design/Environmental Process | 12 | 2009-12-01 | 2010-11-30 19:12 | 2009-12-01 | 2010-11-30 19:12 | 0
| Environmental Permits | 6 | 2010-11-30 19:12 | 2011-06-01 04:48 | 2010-11-30 19:12 | 2011-06-01 04:48 | 0
| ROW/Util/RR Funding Date | 2009-12-01 |  | 2009-12-01 |  | 2011-11-30 14:24 | 24
| ROW/Util/RR | 12 | 2010-11-30 19:12 | 2011-11-30 14:24 | 2010-11-30 19:12 | 2011-11-30 14:24 | 0
| Construction Funding Date | 2009-12-01 |  | 2009-12-01 |  | 2010-11-30 19:12 | 12
| Procurement | 6 | 2010-11-30 19:12 | 2011-06-01 04:48 | 2010-11-30 19:12 | 2011-06-01 04:48 | 0
| Final Design | 6 | 2011-06-01 04:48 | 2011-11-30 14:24 | 2011-06-01 04:48 | 2012-05-05 19:48 | 5.1719
| Construction | 16 | 2011-07-01 14:24 | 2012-11-04 05:24 | 2011-07-06 19:48 | 2012-11-04 05:24 | 0
| Operations & Maintenance | 600 | 2012-10-30 | 2062-10-08 | 2012-10-30 | 2062-10-08
| Replacement | 0 | 2062-10-08 | 2062-10-08 | 2062-10-08 | 2062-10-08
SCHEDULE LAG
| Include Schedule Lag? | Yes
|  | Schedule Lag Parameters - Description | [5 empty] | Months
| Lag A - Time remaining from the finish of Environmental permitting to Lag B | [6 empty] | 0
| Lag B - Time remaining after completion of Environmental Permitting to finish of Procurement | [6 empty] | 0
| Lag C - Lag remaining from finish of Environmental permits to Lag D | [6 empty] | 0
| Lag D - Time remaining after the completion of Environmental Permitting to the completion of ROW/Utilities/RR | [6 empty] | 0
| Lag E - Time remaining to finish ROW/Utilities/RR after the ROW/Utilities/RR funding date | [6 empty] | 0
| Lag F - Time elapsed from the completion of ROW/Utilities/RR to start of Construction | [6 empty] | 6
| Lag G - Time elapsed after the start of Final Design to start of Construction | [6 empty] | 1
| Lag H - Time remaining after the finish of Final Design to finish of Construction | [6 empty] | 6
| Lag I - Time remaining after finish of ROW/UTL/RR to finish of Construction | [6 empty] | 10
| Lag J - Time remaining after finish of ROW/Utilities/RR to Lag K | [6 empty] | 6
| Lag K - Time remaining from finish of ROW/Utilities/RR to finish of Procurement | [6 empty] | 6
BASE COST (in Current Year and Year of Expenditure Dollars)
| Project Phase | Base Cost (CY $M) | Base Cost + Overhead Cost (CY $M) | Base Cost + Overhead Cost (YOE $M)
| Planning |  | 0 | 0 |  | Cost Inflation Rate (percent/year)
| Scoping |  | 0 | 0 |  | Preconstruction |  | 3
| Prelim Design/Environmental Process | 1.19 | 1.1912 | 1.2089 |  | ROW/Utility/RR |  | #NAME?
| Environmental Permits |  | 0.0006 | 0.00062256 |  | Construction |  | #NAME?
| ROW/Util/RR | 3 | 3.0012 | 3.1371
| Procurement |  | 0.0006 | 0.00062256
| Final Design |  | 0.0006 | 0.00063181 |  | Overhead Rate |  | (CY $ M/month)
| Construction | 11.85 | 11.8536 | 12.6704 |  | Preconstruction |  | 0.1
| Total | 16.04 | 16.0478 | 17.0183 |  | Construction |  | 0.225
, | OPERATION, MAINTENANCE & REPLACEMENT
| Facility Performance Period | 50 | years
| Discount Rate to convert CY $ to YOE $ (Net Discount Rate) | 5 | %
|  |  | Operations & Maintenance |  | Replacement |  |  | Agency |  |  | Discruption
| Facility Asset Type | Asset Life Expectancy (yr) | Agency O&M Costs (CY $M/yr) | Disruption (Million-Hr/yr) | Agency Costs (CY $M/event) | Disruption (Million-Hr/event) | NPVValue | nEvent | sumVal | TEmpNPV | nEvent | sumVal | TempNPV
| Asset 1 | 50 |  | 0.028 |  |  | 18.2559 | 1 | 0 | 0 | 1 | 0 | 0 | 0
| Asset 2 | 50 |  |  |  | 0.7 | 18.2559 | 1 | 0 | 0 | 1 | 7 | 6.6667 | 0.7
| Asset 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Asset 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Asset 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total YOE $M |  | 0 | 14 | 0 | 7 |  |  | 0 | 0 |  | 7 | 6.6667 | 0.7
| Total CY $M |  | 0 | 5.1117 | 0 | 6.6667
DISRUPTION
| Disruption Value |  | 10 | $M/M-hr
| Agency/User Cost Discount Factor |  | 1
| Project Phase |  | Disruption
|  | M Veh-Hours/Day | No. of Days | M-Hrs | Cost ($M)
| Planning |  |  | 0 | 0
| Scoping |  |  | 0 | 0
| Prelim Design/Environmental Process |  |  | 0 | 0
| Environmental Permits |  |  | 0 | 0
| ROW/Util/RR | 0.02 | 10 | 0.2 | 2
| Procurement |  |  | 0 | 0
| Final Design |  |  | 0 | 0
| Construction | 0.05 | 10 | 0.5 | 5
| Operations & Maintenance |  |  | 1.4 | 14
| Replacement |  |  | 0.7 | 7
| Total Disruption through OMR |  |  | 2.8 | 28
SUMMARY
| Project Phase | Total CY Cost ($M) | Total YOE Cost ($M) | Duration (months) | Early Start | Early Finish
| Planning | 0 | 0 | 0 | 2009-12-01 | 2009-12-01
| Scoping | 0 | 0 | 0 | 2009-12-01 | 2009-12-01
| Prelim Design/Environmental Process | 1.19 | 1.2089 | 12 | 2009-12-01 | 2010-11-30 19:12
| Environmental Permits | 0 | 0.00062256 | 6 | 2010-11-30 19:12 | 2011-06-01 04:48
| ROW/Util/RR | 3 | 3.1371 | 12 | 2010-11-30 19:12 | 2011-11-30 14:24
| Final Design | 0 | 0.00062256 | 6 | 2011-06-01 04:48 | 2011-11-30 14:24
| Procurement | 0 | 0.00063181 | 6 | 2010-11-30 19:12 | 2011-06-01 04:48
| Construction | 11.85 | 12.6704 | 16 | 2011-07-01 14:24 | 2012-11-04 05:24
| Operations & Maintenance | 0 | 0 | 600 | 2012-11-04 05:24 | 2062-11-04 17:24
| Replacement | 0 | 0 | 0
| Base Cost (YOE $M) | #NAME? | (through Operations, Maintenance, & Replacement)
| Base Construction Completion Date | 2012-11-04 05:24
| Months to Construction Completion | 35.1719
| Base Disruption ($M) | #NAME? | (through Operations, Maintenance, & Replacement)
Formulas:
Early Finish = IF(OR([Early Start]="",[Design-Build]=""),"",[Early Start]+([Design-Build]*30.4))
Early Finish = IF([Design-Build] ="", "",[Design-Build])
Late Start = IF(OR([Late Finish]="",[Design-Build]=""),"",[Late Finish]-([Design-Build]*30.4))
Late Start = INDEX(E20:E30,MATCH([Project Delivery Method],C20:C30,0))
Late Finish = IF([Late Start, row below] = "", "",[Late Start, row below])
Late Finish = IF(OR([Late Start, row below]="",G26="",G28=""),"",MIN([Late Start, row below],G26,G28))
Early Start = IF([Early Finish, row above]="","",[Early Finish, row above])
Early Start = IF(OR([Early Finish, row above]="",F21=""),"",MAX([Early Finish, row above],F21))
Analysis
Schedule
Lag
Cost
OMR
Disruption
Create Project
Button 8

## 2 - Risk Identification
SHRP2 Risk Management Template (Montecarlo Approach)
Step 02 - Risk Identification
Risk Label | Description of Risk Table Below Fills by Selecting "Create List of Risks" Button Above | Project Phase | Retire Risk?
PL-1 | Project funding delayed or reduced. PL | Planning | No
PL-2 | Opposition to removing access to US-555 fro 12th St. | Planning | No
PL-3 | Opposition to "splitting" alignment of SH-111 in the interchange area. | Planning | No
PL-4 | Other stakeholder issues not captured separately. | Planning | No
SC-1 | Change in East-West project limits. | Scoping | No
SC-2 | Change in North-South project limits. | Scoping | No
SC-3 | Additional local improvements required. | Scoping | No
SC-4 | Increased aestethetics for US-555/SH-111 interchange. | Scoping | No
SC-5 | Replace culvert over Wandering Creek. | Scoping | No
SC-6 | Provide new lighting throughout project. | Scoping | No
SC-7 | ITS added to this project. | Scoping | No
PD-1 | Shift alignment of US 555 at east end of project | Prelim Design/Environmental Process | No
PD-2 | Split alignment of SH-111 at US-555 interchange. | Prelim Design/Environmental Process | No
PD-3 | Change in configuration of SH 111 / US 555 interchange. | Prelim Design/Environmental Process | No
PD-4 | Ground improvement required in interchange area. | Prelim Design/Environmental Process | No
PD-5 | Shoulders required on US-555. | Prelim Design/Environmental Process | No
PD-6 | Shoulders required on SH-111. | Prelim Design/Environmental Process | No
PD-7 | Additional cost for signalized intersections. | Prelim Design/Environmental Process | No
PD-8 | Change in pavement section and/or type. | Prelim Design/Environmental Process | No
PD-9 | Rehabilitate instead of reconstruct existing roadway (e.g., overlay instead). | Prelim Design/Environmental Process | No
PD-10 | Change in stormwater design standards. | Prelim Design/Environmental Process | No
PD-11 | Cannot use City sewer system for project runoff (or City charges for use). | Prelim Design/Environmental Process | No
PD-12 | Structures impacted by Main Street realignment are eligible for Historic Register. | Prelim Design/Environmental Process | No
PD-13 | Change in environmental documentation. | Prelim Design/Environmental Process | No
PD-14 | Delays completing environmental documentation. | Prelim Design/Environmental Process | No
PD-15 | Encounter unanticipated contamination in interchange area. | Prelim Design/Environmental Process | No
PD-16 | Additional wetland mitigation required for planned alignment. | Prelim Design/Environmental Process | No
EP-1 | Challenge to environmental determination or permits | Environmental Permits | No
EP-2 | Delay obtaining the 404 permit | Environmental Permits | No
RR-1 | Uncertainty in ROW inflation rate | ROW/Util/RR | No
RR-2 | Accelerating pace of development in interchange area | ROW/Util/RR | No
RR-3 | Unwilling sellers | ROW/Util/RR | No
RR-4 | Additional relocation or demolition required | ROW/Util/RR | No
RR-5 | Additional ROW required for planned project | ROW/Util/RR | No
RR-6 | Other delays to ROW planning | ROW/Util/RR | No
RR-7 | Telecom utility wants a cost-sharing agreement | ROW/Util/RR | No
RR-8 | QDOT helps City pay for water and sewer-line relocation | ROW/Util/RR | No
RR-9 | Other utility relocations not completed on time | ROW/Util/RR | No
RR-10 | Damage existing utility or encounter unanticipated utility during construction | ROW/Util/RR | No
PR-1 | Uncertainty in construction-cost inflation rate | Procurement | No
PR-2 | Uncertain Design/Build contracting market conditions at time of bid | Procurement | No
PR-3 | Material-supply issues | Procurement | No
PR-4 | Change in project delivery method | Procurement | No
PR-5 | Accelerate pre-construction activities to reach NTP sooner | Procurement | No
PR-6 | Use incentives to accelerate D/B construction | Procurement | No
PR-7 | Issues with D/B design or submittals | Procurement | No
PR-8 | Other problems with D/B contract procurement | Procurement | No
CR-1 | D/B construction phasing significantly different than assumed | Construction | No
CR-2 | Additional Maintenance of Traffic required | Construction | No
CR-3 | Problems with planned accelerated bridge construction (ABC) technique | Construction | No
CR-4 | Unable to construct interchange embankments as rapidly as assumed | Construction | No
CR-5 | Difficult foundation installation | Construction | No
CR-6 | Severe weather event significantly impacts construction | Construction | No
CR-7 | Colder-than-usual winter | Construction | No
CR-8 | Significant accident during construction | Construction | No
CR-9 | Limited construction staging area in vicinity of interchange | Construction | No
CR-10 | Fish window in Wandering Creek | Construction | No
CR-11 | Non-compliance with permits during construction | Construction | No
CR-12 | Extended overheads as a function of project delays | Construction | No
Create List of Risks
Clear All

## 3 - Risk Assessment
SHRP2 Risk Management Template (Montecarlo Approach)
Step 03 - Risk Assessment
Risk |  | Probability | Risk Type | Cost |  |  | Duration |  |  | Disruptions
Label | Risk Description |  |  | Cost Impact | Affected Phase | Impact | Duraction Impact | Affected Phase | Impact | Duraction Impact | Affected Phase | Impact
PL-1 | Project funding delayed or reduced. PL |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PL-2 | Opposition to removing access to US-555 fro 12th St. | #NAME? | Threat | #NAME? | Construction | #NAME? |  |  | #NAME? |  |  | #NAME? | #NAME?
PL-3 | Opposition to "splitting" alignment of SH-111 in the interchange area. |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PL-4 | Other stakeholder issues not captured separately. |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
SC-1 | Change in East-West project limits. |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
SC-2 | Change in North-South project limits. |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
SC-3 | Additional local improvements required. | #NAME? | Threat | #NAME? | Construction | #NAME? | #NAME? | Prelim Design/Environmental Process | #NAME? |  |  | #NAME? | #NAME?
SC-4 | Increased aestethetics for US-555/SH-111 interchange. |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
SC-5 | Replace culvert over Wandering Creek. | #NAME? | Threat | #NAME? | Construction | #NAME? |  |  | #NAME? |  |  | #NAME? | #NAME?
SC-6 | Provide new lighting throughout project. | #NAME? | Threat | #NAME? | Construction | #NAME? |  |  | #NAME? |  |  | #NAME? | #NAME?
SC-7 | ITS added to this project. |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PD-1 | Shift alignment of US 555 at east end of project | #NAME? | Threat | #NAME? | ROW/Util/RR | #NAME? | #NAME? | ROW/Util/RR | #NAME? |  |  | #NAME? | #NAME?
PD-2 | Split alignment of SH-111 at US-555 interchange. |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PD-3 | Change in configuration of SH 111 / US 555 interchange. |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PD-4 | Ground improvement required in interchange area. | #NAME? | Threat | #NAME? | Construction | #NAME? | #NAME? | Construction | #NAME? |  |  | #NAME? | #NAME?
PD-5 | Shoulders required on US-555. | #NAME? | Threat | #NAME? | Construction | #NAME? | 2.5 | Construction | #NAME? |  |  | #NAME? | #NAME?
PD-6 | Shoulders required on SH-111. | #NAME? | Threat | #NAME? | Construction | #NAME? | 2.5 | Construction | #NAME? |  |  | #NAME? | #NAME?
PD-7 | Additional cost for signalized intersections. |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PD-8 | Change in pavement section and/or type. | #NAME? | Opportunity | 1.05 | Construction | #NAME? |  |  | #NAME? |  |  | #NAME? | #NAME?
PD-9 | Rehabilitate instead of reconstruct existing roadway (e.g., overlay instead). |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PD-10 | Change in stormwater design standards. |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PD-11 | Cannot use City sewer system for project runoff (or City charges for use). | #NAME? | Threat | #NAME? | ROW/Util/RR | #NAME? | 0.625 | ROW/Util/RR | #NAME? |  |  | #NAME? | #NAME?
PD-12 | Structures impacted by Main Street realignment are eligible for Historic Register. | 0.125 | Threat | 1.05 | ROW/Util/RR | 0.13125 | 2.5 | ROW/Util/RR | 0.3125 |  |  | 0 | #NAME?
PD-13 | Change in environmental documentation. | 0.125 | Threat | 1.05 | Prelim Design/Environmental Process | 0.13125 | 8 | Prelim Design/Environmental Process | 1 |  |  | 0 | #NAME?
PD-14 | Delays completing environmental documentation. | 0.3 |  |  |  | 0 | 2.5 | Prelim Design/Environmental Process | 0.75 |  |  | 0 | #NAME?
PD-15 | Encounter unanticipated contamination in interchange area. | 0.3 | Threat | 0.1 | Construction | 0.03 |  |  | 0 |  |  | 0 | #NAME?
PD-16 | Additional wetland mitigation required for planned alignment. | 0.3 | Threat | 0.35 | Construction | 0.105 |  |  | 0 |  |  | 0 | #NAME?
EP-1 | Challenge to environmental determination or permits |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
EP-2 | Delay obtaining the 404 permit | 0.125 |  |  |  | 0 | 2.5 | Environmental Permits | 0.3125 |  |  | 0 | #NAME?
RR-1 | Uncertainty in ROW inflation rate | 0.55 | Threat | 1.05 | ROW/Util/RR | 0.5775 |  |  | 0 |  |  | 0 | #NAME?
RR-2 | Accelerating pace of development in interchange area | 0.3 | Threat | 1.05 | ROW/Util/RR | 0.315 | #NAME? | ROW/Util/RR | #NAME? |  |  | 0 | #NAME?
RR-3 | Unwilling sellers | 0.55 | Threat | 1.05 | ROW/Util/RR | 0.5775 |  |  | 0 |  |  | 0 | #NAME?
RR-4 | Additional relocation or demolition required |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
RR-5 | Additional ROW required for planned project |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
RR-6 | Other delays to ROW planning | 0.3 |  |  |  | 0 | 0.625 | ROW/Util/RR | 0.1875 |  |  | 0 | #NAME?
RR-7 | Telecom utility wants a cost-sharing agreement | 0.3 | Threat | 0.35 | ROW/Util/RR | 0.105 |  |  | 0 |  |  | 0 | #NAME?
RR-8 | QDOT helps City pay for water and sewer-line relocation | 0.55 | Threat | 1.05 | ROW/Util/RR | 0.5775 |  |  | 0 |  |  | 0 | #NAME?
RR-9 | Other utility relocations not completed on time |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
RR-10 | Damage existing utility or encounter unanticipated utility during construction |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PR-1 | Uncertainty in construction-cost inflation rate | #NAME? | Threat | 1.05 | Construction | #NAME? |  |  | #NAME? |  |  | #NAME? | #NAME?
PR-2 | Uncertain Design/Build contracting market conditions at time of bid | 0.25 | Threat | #NAME? | Construction | #NAME? | 1 | Procurement | 0.25 |  |  | 0 | #NAME?
PR-3 | Material-supply issues |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PR-4 | Change in project delivery method |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PR-5 | Accelerate pre-construction activities to reach NTP sooner |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PR-6 | Use incentives to accelerate D/B construction |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
PR-7 | Issues with D/B design or submittals | 0.3 | Threat |  |  | 0 | 2.5 | Final Design | 0.75 |  |  | 0 | #NAME?
PR-8 | Other problems with D/B contract procurement | #NAME? | Threat |  |  | #NAME? | 0.625 | Procurement | #NAME? |  |  | #NAME? | #NAME?
CR-1 | D/B construction phasing significantly different than assumed | #NAME? | Opportunity |  |  | #NAME? | 2 | Construction | #NAME? | #NAME? | Construction | #NAME? | #NAME?
CR-2 | Additional Maintenance of Traffic required | 0.55 | Threat | #NAME? | Construction | #NAME? | 0.125 | Construction | 0.06875 |  |  | 0 | #NAME?
CR-3 | Problems with planned accelerated bridge construction (ABC) technique | 0.55 | Threat | 0.35 | Construction | 0.1925 | 0.625 | Construction | 0.34375 |  |  | 0 | #NAME?
CR-4 | Unable to construct interchange embankments as rapidly as assumed | 0.3 | Threat | 0.35 | Construction | 0.105 | 2.5 | Construction | 0.75 |  |  | 0 | #NAME?
CR-5 | Difficult foundation installation | 0.125 | Threat | 0.35 | Construction | 0.04375 | 0.625 | Construction | 0.078125 |  |  | 0 | #NAME?
CR-6 | Severe weather event significantly impacts construction |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
CR-7 | Colder-than-usual winter | 0.125 |  |  |  | 0 | 0.125 | Construction | 0.015625 |  |  | 0 | #NAME?
CR-8 | Significant accident during construction |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
CR-9 | Limited construction staging area in vicinity of interchange | 0.3 | Threat | 0.1 | Construction | 0.03 |  |  | 0 |  |  | 0 | #NAME?
CR-10 | Fish window in Wandering Creek |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
CR-11 | Non-compliance with permits during construction |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
CR-12 | Extended overheads as a function of project delays |  |  |  |  | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
[6 empty] | 0 |  |  | 0 |  |  | 0 | #NAME?
`

## 4 - Full Dashboard
SHRP2 Risk Management Template (Montecarlo Approach)
Project Performance
Schedule Duration Assumption:
Some risks in a phase will occur concurrently, while others will occur sequentially.
Project Cost, Duration, and Disruption Performance
Project Phase | Base |  |  |  | Risk |  |  | Total (Base + Risk)
| Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (YOE $M)
Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ConstEs | 0 | 0
Scoping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ConsBES | 0 | 0
Prelim Design/Environmental Process | 1.19 | 12 | 0 | 0.13125 | 1.9375 | 0 | 1.3213 | 13.9375 | 0 | 1.3213 |  | ConstEF | 0.13125 | 1.9375
Environmental Permits | 0 | 6 | 0 | 0 | 0.3125 | 0 | 0 | 6.3125 | 0 | 0 |  | ConstBEF | 0 | 0.3125
ROW/Util/RR | 3 | 12 | 0.2 | 2.625 | 1.5 | 0 | 5.625 | 13.5 | 0.2 | 5.825 |  | PlanES | 2.625 | 1.5 | 1.125
Final Design | 0 | 6 | 0 | 0 | 0.75 | 0 | 0 | 6.75 | 0 | 0 |  | PlaBES | 0 | 0.75 | 0.75
Procurement | 0 | 6 | 0 | 0 | 0.32812 | 0 | 0 | 6.3281 | 0 | 0 |  |  | 0 | 0.32812 | 0.28906
Construction | 11.85 | 16 | 0.5 | 2.3287 | 0.95937 | -0.025 | 14.1788 | 16.9594 | 0.475 | 14.6538 |  | PreC0nstDelay | 2.3287 | 0.95937 | 0.85469
Operations & Maintenance | 0 | 600 | 1.4 | 0 | 0 | 0 | 0 | 600 | 1.4 | 1.4 |  | ConsDelay | 0 | 0 | 0
Replacement | 0 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0.7 |  |  | PreConstDelay | 0 | 0
Total | 16.04 |  | 2.8 | #NAME? |  | -0.025 | #NAME? |  | 2.775 | #NAME? |  | ConsDelay
Project Schedule Performance (Base vs. Risk Eval)
Project Phase |  |  | Base Project Schedule Performance | [5 empty] | Project Schedule Performance
| Duration (Months/Date) | Early Start | Early Finish | Late Start | Late Finish | Float (months) | Duration (Months / Date) | Early Start | Early Finish | Late Start | Late Finish | Float (months)
Planning | 0 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 0 | 0 | 2009-12-01 | 2009-12-01 | 2009-11-05 08:24 | 2009-11-05 08:24 | -0.84375
Scoping | 0 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 2009-12-01 | 0 | 0 | 2009-12-01 | 2009-12-01 | 2009-11-05 08:24 | 2009-11-05 08:24 | -0.84375
Design Funding Date | 2009-12-01 | 0 | 2009-12-01 | 0 | 2009-12-01 | 0 | 2009-12-01 |  | 2009-12-01 |  | 2009-11-05 08:24 | -0.84375
Prelim Design/Environmental Process | 12 | 2009-12-01 | 2010-11-30 19:12 | 2009-12-01 | 2010-11-30 19:12 | 0 | 13.9375 | 2009-12-01 | 2011-01-28 16:48 | 2009-11-05 08:24 | 2011-01-03 01:12 | -0.84375
Environmental Permits | 6 | 2010-11-30 19:12 | 2011-06-01 04:48 | 2010-11-30 19:12 | 2011-06-01 04:48 | 0 | 6.3125 | 2011-01-28 16:48 | 2011-08-08 14:24 | 2011-02-08 03:36 | 2011-08-19 01:12 | 0.34375
ROW/Util/RR Funding Date | 2009-12-01 | 0 | 2009-12-01 | 0 | 2011-11-30 14:24 | 1900-01-23 | 2009-12-01 |  | 2009-12-01 |  | 2012-02-17 10:48 | 26.5937
ROW/Util/RR | 12 | 2010-11-30 19:12 | 2011-11-30 14:24 | 2010-11-30 19:12 | 2011-11-30 14:24 | 0 | 13.5 | 2011-01-28 16:48 | 1900-01-12 12:00 | 2011-01-03 01:12 | 2012-02-17 10:48 | 1346.8076
Construction Funding Date | 2009-12-01 | 0 | 2009-12-01 | 0 | 2010-11-30 19:12 | 1900-01-11 | 2009-12-01 |  | 2009-12-01 |  | 2011-01-25 20:24 | 13.8438
Procurement | 6 | 2010-11-30 19:12 | 2011-06-01 04:48 | 2010-11-30 19:12 | 2011-06-01 04:48 | 0 | 6.75 | 2011-01-28 16:48 | 2011-08-19 01:12 | 2011-01-25 20:24 | 2011-08-19 01:12 | 0
Final Design | 6 | 2011-06-01 04:48 | 2011-11-30 14:24 | 2011-06-01 04:48 | 2012-05-05 19:48 | 1900-01-04 04:07 | 6.3281 | 2011-08-19 01:12 | 2012-02-27 10:12 | 2011-08-19 01:12 | 2012-08-13 10:23 | 5.5266
Construction | 16 | 2011-07-01 14:24 | 2012-11-04 05:24 | 2011-07-06 19:48 | 2012-11-04 05:24 | 0 | 16.9594 | 2011-09-18 10:48 | 2013-02-15 00:22 | 2011-09-18 10:48 | 2013-02-15 00:22 | 0
Operations & Maintenance | 600 | 2012-10-30 | 2062-10-08 | 2012-10-30 | 2062-10-08 |  | 600 | 2013-02-15 00:22 | 2063-01-24 00:22 | 2013-02-15 00:22 | 2063-01-24 00:22
Replacement | 0 | 2062-10-08 | 2062-10-08 | 2062-10-08 | 2062-10-08 |  | 0 | 2063-01-24 00:22 | 2063-01-24 00:22 | 2063-01-24 00:22 | 2063-01-24 00:22
Project Start Date | 2009-12-01 | [5 empty] | 2009-12-01 |  |  |  |  | Total
Construction Finish Date | 2012-11-04 05:24 | [5 empty] | 2013-02-15 00:22
Project Duration (months) | 35.1719 | [5 empty] | #NAME?
Formulas:
Disruption (M-hrs) = IF(OR([Total (Base + Risk)]="",[Cost (CY $M)]=""),"",[Total (Base + Risk)]+([Cost (CY $M)]*30.4))
Disruption (M-hrs) = IF([Cost (CY $M)] ="", "",[Cost (CY $M)])
Cost (CY $M) = [Base]
Total (Base + Risk) = [Duration (months)]
Total (Base + Risk) = IF([Disruption (M-hrs), row above]="","",[Disruption (M-hrs), row above])
Cost (YOE $M) = IF(OR([Late Finish]="",[Cost (CY $M)]=""),"",[Late Finish]-([Cost (CY $M)]*30.4))
Late Finish = IF([Cost (YOE $M), row below] = "", "",[Cost (YOE $M), row below])
Late Finish = IF(OR([Cost (YOE $M), row below]="",K31="",K33=""),"",MIN([Cost (YOE $M), row below],K31,K33))

## RiskSerializationData8 (hidden)
Written By Version | 8.2.2
Serialization Major Version | 4
Serialization Minor Version | 0
Browse Record | Display Mode | Sens Graph Type | Cond Sens Settings | Scenario Settings | Selected Scenario | Distribution Options | Distribution GS | Distribution Curves | Sens Tornado Options | Sens Tornado GS | Sens Tornado Curves | Scen Tornado Options | Scen Tornado GS | Scen Tornado Curves | Sens Spider Option | Sens Spider GS | Sens Spider Curves
#NAME? | 1 | 3 |  |  | 0
#NAME? | 1 | 3 |  |  | 0
#NAME? | 1 | 3 |  |  | 0
#NAME? | 1 | 3 |  |  | 0 |  |  |  | 3,10,2,.95,5,16,FALSE,0,TRUE,TRUE,TRUE | GF1_4VKXXwEAEwBSAQwjACcANgB3AIcAiACWAKQAAAAAAEoBKAD//wAAAQEEAAAAAAQwLjAwAAAAARVUb3RhbCAvIENvc3QgIChDWSAkTSkBJklucHV0cyBSYW5rZWQgYnkgRWZmZWN0IG9uIE91dHB1dCBNZWFuAQEMAAEAAQZMZWdlbmQDAAEA/wEBAQEBAAEBAQAEAAAAAQEBAQEAAQEBAAQAAAAKwwAI5wAI8gAI/QAICAEIEwEIHgEIKQEINAEIPwEIIgAVVG90YWwgLyBDb3N0ICAoQ1kgJE0pAAAA/9wUPAEAAAIACQAAAAElAQAAAgAJAAAAAk8BAAACAAkAAAADjAEAAAIACQAAAARMAQAAAgAJAAAABTkBAAACAAkAAAAGTgEAAAIACQAAAAcjAQAAAgAJAAAACCkBAAACAAkAAAAJYAEAAAIABQABAQEAAAE= | #NAME?
#NAME? | 0 | 3 |  |  | 0 | TRUE | GF1_rK0qDwEAEwB0AQwjACcAPACkALgAuQDHANUATgFwAWoBKwD//wAAAAAAAAEEAAAAAAdHZW5lcmFsAAAAATpPdGhlciBwcm9ibGVtcyB3aXRoIEQvQiBjb250cmFjdCBwcm9jdXJlbWVudCAvIFByb2JhYmlsaXR5AShDb21wYXJpc29uIHdpdGggUmlza05vcm1hbCgwLjEyNSwwLjAxMjUpAQEQAAIAAQpTdGF0aXN0aWNzAwEBAP8BAQEBAQABAQEABAAAAAEBAQEBAAEBAQAEAAAAAtwAAicBAEcAOk90aGVyIHByb2JsZW1zIHdpdGggRC9CIGNvbnRyYWN0IHByb2N1cmVtZW50IC8gUHJvYmFiaWxpdHkAAAD/AAD/AQAAAgACACUAGFJpc2tOb3JtYWwoMC4xMjUsMC4wMTI1KQABAP8AAAABAAACAFYBYAEBAQMBmpmZmZmZqT8AAGZmZmZmZu4/AAAFAAEBAQABAQEA | #NAME?

## 4 - Summary Dashboard
SHRP2 Risk Management Template (Montecarlo Approach)
Step 03 - Project Dashboard
Uncertainty | Cost
| Total Base Cost | 16.04
| Base Cost + Overhead Cost (YOE $M) | 17.0183
Risk
| Risk Cost | 5.085
| Total Base Cost + Risk | 21.125
Uncertainty | Duration
| Start Project | 2009-12-01
| Construction Finish Date | 2012-11-04 05:24
| Total Duration | 35.1719
Risk | Start Project | 2009-12-01
| Construction Finish Date | 2013-02-15 00:22
| Total Duration | 38.5531
Add Automatic Output Definitions

## Summary Outputs
Outputs
|  | Report: |  | Summary Statistics Report
|  | Performed By: |  | abast
|  | Date: |  | Friday, September 30, 2022
Summary Statistics
Output | Cell | Graphs | Function |  | Minimum | Maximum | Mean | Std Dev | 5% | 95%
Base Cost (YOE $M) / Total CY Cost ($M) | '1 - Project Structuring'!D110 |  | RiskOutput() |  | 16.7434 | 17.265 | 17.0184 | 0.083968 | 16.8797 | 17.1572
Base Disruption ($M) / Total CY Cost ($M) | '1 - Project Structuring'!D113 |  | RiskOutput() |  | 18.7783 | 18.7783 | 18.7783 | 0 | 18.7783 | 18.7783
Total / Cost (CY $M) | '4 - Full Dashboard'!E19 |  | RiskOutput() |  | 4.7651 | 5.3748 | 5.085 | 0.098281 | 4.9137 | 5.2428
Total / Cost (CY $M) | '4 - Full Dashboard'!H19 |  | RiskOutput() |  | 20.8051 | 21.4148 | 21.125 | 0.098281 | 20.9537 | 21.2828
Total / Cost (YOE $M) | '4 - Full Dashboard'!K19 |  | RiskOutput() |  | 22.8772 | 23.4941 | 23.2 | 0.098329 | 23.0262 | 23.3574
Project Duration (months) / Duration (Months / Date) | '4 - Full Dashboard'!H40 |  | RiskOutput() |  | 38.3992 | 38.7174 | 38.5531 | 0.051569 | 38.4665 | 38.6372
Base Cost + Overhead Cost (YOE $M) / Cost | '4 - Summary Dashboard'!E10 |  | RiskOutput() |  | 16.7434 | 17.265 | 17.0184 | 0.083968 | 16.8797 | 17.1572
Risk Cost / Cost | '4 - Summary Dashboard'!E12 |  | RiskOutput() |  | 4.7651 | 5.3748 | 5.085 | 0.098281 | 4.9137 | 5.2428
Total Base Cost + Risk / Cost | '4 - Summary Dashboard'!E13 |  | RiskOutput() |  | 20.8051 | 21.4148 | 21.125 | 0.098281 | 20.9537 | 21.2828
Total Duration / Duration | '4 - Summary Dashboard'!E20 |  | RiskOutput() |  | 35.1719 | 35.1719 | 35.1719 | 0 | 35.1719 | 35.1719
Total Duration / Duration | '4 - Summary Dashboard'!E23 |  | RiskOutput() |  | 38.3992 | 38.7174 | 38.5531 | 0.051569 | 38.4665 | 38.6372

## Summary Inputs
Inputs
|  | Report: |  | Summary Statistics Report
|  | Performed By: |  | abast
|  | Date: |  | Friday, September 30, 2022
Summary Statistics
Input | Cell | Graphs | Function |  | Minimum | Maximum | Mean | Std Dev | 5% | 95%
ROW/Utility/RR / Months | '1 - Project Structuring'!J55 |  | RiskNormal(3,0.3,RiskStatic(3)) |  | 1.9528 | 4.1246 | 3.0001 | 0.30071 | 2.5042 | 3.4918
Construction / Months | '1 - Project Structuring'!J56 |  | RiskNormal(3,0.3,RiskStatic(3)) |  | 1.9482 | 3.9478 | 2.9999 | 0.30024 | 2.5065 | 3.4932
Cell AZ9 | '3 - Risk Assessment'!AZ9 |  | RiskCompound(D9,G9) |  | 0 | 0 | 0 | 0 | 0 | 0
Opposition to removing access to US-555 fro 12th St. / Probability | '3 - Risk Assessment'!D10 |  | RiskNormal(0.125,0.0125,RiskStatic(0.125)) |  | 0.077903 | 0.16499 | 0.125 | 0.012513 | 0.10438 | 0.1455
Cell AZ10 | '3 - Risk Assessment'!AZ10 |  | RiskCompound(D10,G10) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ11 | '3 - Risk Assessment'!AZ11 |  | RiskCompound(D11,G11) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ12 | '3 - Risk Assessment'!AZ12 |  | RiskCompound(D12,G12) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ13 | '3 - Risk Assessment'!AZ13 |  | RiskCompound(D13,G13) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ14 | '3 - Risk Assessment'!AZ14 |  | RiskCompound(D14,G14) |  | 0 | 0 | 0 | 0 | 0 | 0
Additional local improvements required. / Probability | '3 - Risk Assessment'!D15 |  | RiskNormal(0.3,0.03,RiskStatic(0.3)) |  | 0.19549 | 0.39917 | 0.29999 | 0.030013 | 0.25055 | 0.34918
Construction / Duraction Impact | '3 - Risk Assessment'!K15 |  | RiskNormal(0.625,0.0625,RiskStatic(0.625)) |  | 0.42509 | 0.82147 | 0.625 | 0.062444 | 0.52201 | 0.72749
Cell AZ15 | '3 - Risk Assessment'!AZ15 |  | RiskCompound(D15,G15) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ16 | '3 - Risk Assessment'!AZ16 |  | RiskCompound(D16,G16) |  | 0 | 0 | 0 | 0 | 0 | 0
Replace culvert over Wandering Creek. / Probability | '3 - Risk Assessment'!D17 |  | RiskNormal(0.3,0.03,RiskStatic(0.3)) |  | 0.20422 | 0.39614 | 0.3 | 0.029995 | 0.25059 | 0.34932
Cell AZ17 | '3 - Risk Assessment'!AZ17 |  | RiskCompound(D17,G17) |  | 0 | 0 | 0 | 0 | 0 | 0
Provide new lighting throughout project. / Probability | '3 - Risk Assessment'!D18 |  | RiskNormal(0.55,0.055,RiskStatic(0.55)) |  | 0.35012 | 0.72762 | 0.54997 | 0.055034 | 0.45912 | 0.64007
Cell AZ18 | '3 - Risk Assessment'!AZ18 |  | RiskCompound(D18,G18) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ19 | '3 - Risk Assessment'!AZ19 |  | RiskCompound(D19,G19) |  | 0 | 0 | 0 | 0 | 0 | 0
Shift alignment of US 555 at east end of project / Probability | '3 - Risk Assessment'!D20 |  | RiskNormal(0.025,0.0025,RiskStatic(0.025)) |  | 0.016952 | 0.033302 | 0.025001 | 0.002501 | 0.020878 | 0.029091
ROW/Util/RR / Duraction Impact | '3 - Risk Assessment'!K20 |  | RiskNormal(2.5,0.25,RiskStatic(2.5)) |  | 1.6506 | 3.3484 | 2.5 | 0.25029 | 2.0883 | 2.911
Cell AZ20 | '3 - Risk Assessment'!AZ20 |  | RiskCompound(D20,G20) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ21 | '3 - Risk Assessment'!AZ21 |  | RiskCompound(D21,G21) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ22 | '3 - Risk Assessment'!AZ22 |  | RiskCompound(D22,G22) |  | 0 | 0 | 0 | 0 | 0 | 0
Ground improvement required in interchange area. / Probability | '3 - Risk Assessment'!D23 |  | RiskNormal(0.125,0.0125,RiskStatic(0.125)) |  | 0.080906 | 0.16783 | 0.125 | 0.012514 | 0.10435 | 0.14545
Construction / Duraction Impact | '3 - Risk Assessment'!K23 |  | RiskNormal(0.625,0.0625,RiskStatic(0.625)) |  | 0.42982 | 0.90219 | 0.62509 | 0.062755 | 0.52165 | 0.72745
Cell AZ23 | '3 - Risk Assessment'!AZ23 |  | RiskCompound(D23,G23) |  | 0 | 0 | 0 | 0 | 0 | 0
Shoulders required on US-555. / Probability | '3 - Risk Assessment'!D24 |  | RiskNormal(0.025,0.0025,RiskStatic(0.025)) |  | 0.016813 | 0.033487 | 0.025001 | 0.0025018 | 0.020886 | 0.029097
Cell AZ24 | '3 - Risk Assessment'!AZ24 |  | RiskCompound(D24,G24) |  | 0 | 0 | 0 | 0 | 0 | 0
Shoulders required on SH-111. / Probability | '3 - Risk Assessment'!D25 |  | RiskNormal(0.025,0.0025,RiskStatic(0.025)) |  | 0.016127 | 0.033749 | 0.025 | 0.0025044 | 0.020869 | 0.029109
Cell AZ25 | '3 - Risk Assessment'!AZ25 |  | RiskCompound(D25,G25) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ26 | '3 - Risk Assessment'!AZ26 |  | RiskCompound(D26,G26) |  | 0 | 0 | 0 | 0 | 0 | 0
Change in pavement section and/or type. / Probability | '3 - Risk Assessment'!D27 |  | RiskNormal(0.3,0.03,RiskStatic(0.3)) |  | 0.2059 | 0.39484 | 0.3 | 0.029958 | 0.2505 | 0.34932
Cell AZ27 | '3 - Risk Assessment'!AZ27 |  | RiskCompound(D27,G27) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ28 | '3 - Risk Assessment'!AZ28 |  | RiskCompound(D28,G28) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ29 | '3 - Risk Assessment'!AZ29 |  | RiskCompound(D29,G29) |  | 0 | 0 | 0 | 0 | 0 | 0
PD-11 / Probability | '3 - Risk Assessment'!D30 |  | RiskNormal(0.3,0.03,RiskStatic(0.3)) |  | 0.20072 | 0.40046 | 0.3 | 0.030014 | 0.25039 | 0.34929
Cell AZ30 | '3 - Risk Assessment'!AZ30 |  | RiskCompound(D30,G30) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ31 | '3 - Risk Assessment'!AZ31 |  | RiskCompound(D31,G31) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ32 | '3 - Risk Assessment'!AZ32 |  | RiskCompound(D32,G32) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ33 | '3 - Risk Assessment'!AZ33 |  | RiskCompound(D33,G33) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ34 | '3 - Risk Assessment'!AZ34 |  | RiskCompound(D34,G34) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ35 | '3 - Risk Assessment'!AZ35 |  | RiskCompound(D35,G35) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ36 | '3 - Risk Assessment'!AZ36 |  | RiskCompound(D36,G36) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ37 | '3 - Risk Assessment'!AZ37 |  | RiskCompound(D37,G37) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ38 | '3 - Risk Assessment'!AZ38 |  | RiskCompound(D38,G38) |  | 0 | 0 | 0 | 0 | 0 | 0
ROW/Util/RR / Duraction Impact | '3 - Risk Assessment'!K39 |  | RiskNormal(2.5,0.25,RiskStatic(2.5)) |  | 1.696 | 3.3029 | 2.5 | 0.24985 | 2.0878 | 2.9107
Cell AZ39 | '3 - Risk Assessment'!AZ39 |  | RiskCompound(D39,G39) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ40 | '3 - Risk Assessment'!AZ40 |  | RiskCompound(D40,G40) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ41 | '3 - Risk Assessment'!AZ41 |  | RiskCompound(D41,G41) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ42 | '3 - Risk Assessment'!AZ42 |  | RiskCompound(D42,G42) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ43 | '3 - Risk Assessment'!AZ43 |  | RiskCompound(D43,G43) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ44 | '3 - Risk Assessment'!AZ44 |  | RiskCompound(D44,G44) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ45 | '3 - Risk Assessment'!AZ45 |  | RiskCompound(D45,G45) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ46 | '3 - Risk Assessment'!AZ46 |  | RiskCompound(D46,G46) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ47 | '3 - Risk Assessment'!AZ47 |  | RiskCompound(D47,G47) |  | 0 | 0 | 0 | 0 | 0 | 0
Uncertainty in construction-cost inflation rate / Probability | '3 - Risk Assessment'!D48 |  | RiskNormal(0.55,0.055,RiskStatic(0.55)) |  | 0.37236 | 0.73677 | 0.55001 | 0.054969 | 0.45949 | 0.64007
Cell AZ48 | '3 - Risk Assessment'!AZ48 |  | RiskCompound(D48,G48) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ49 | '3 - Risk Assessment'!AZ49 |  | RiskCompound(D49,G49) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ50 | '3 - Risk Assessment'!AZ50 |  | RiskCompound(D50,G50) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ51 | '3 - Risk Assessment'!AZ51 |  | RiskCompound(D51,G51) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ52 | '3 - Risk Assessment'!AZ52 |  | RiskCompound(D52,G52) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ53 | '3 - Risk Assessment'!AZ53 |  | RiskCompound(D53,G53) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ54 | '3 - Risk Assessment'!AZ54 |  | RiskCompound(D54,G54) |  | 0 | 0 | 0 | 0 | 0 | 0
Other problems with D/B contract procurement / Probability | '3 - Risk Assessment'!D55 |  | RiskNormal(0.125,0.0125,RiskStatic(0.125)) |  | 0.086061 | 0.16637 | 0.125 | 0.012492 | 0.10434 | 0.14548
Cell AZ55 | '3 - Risk Assessment'!AZ55 |  | RiskCompound(D55,G55) |  | 0 | 0 | 0 | 0 | 0 | 0
CR-1 / Probability | '3 - Risk Assessment'!D56 |  | RiskNormal(0.25,0.025,RiskStatic(0.25)) |  | 0.16979 | 0.32936 | 0.25 | 0.024974 | 0.20867 | 0.29102
Construction | '3 - Risk Assessment'!O56 |  | RiskNormal(0.1,0.01,RiskStatic(0.1)) |  | 0.066947 | 0.1328 | 0.099999 | 0.010006 | 0.083458 | 0.11638
Cell AZ56 | '3 - Risk Assessment'!AZ56 |  | RiskCompound(D56,G56) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ57 | '3 - Risk Assessment'!AZ57 |  | RiskCompound(D57,G57) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ58 | '3 - Risk Assessment'!AZ58 |  | RiskCompound(D58,G58) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ59 | '3 - Risk Assessment'!AZ59 |  | RiskCompound(D59,G59) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ60 | '3 - Risk Assessment'!AZ60 |  | RiskCompound(D60,G60) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ61 | '3 - Risk Assessment'!AZ61 |  | RiskCompound(D61,G61) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ62 | '3 - Risk Assessment'!AZ62 |  | RiskCompound(D62,G62) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ63 | '3 - Risk Assessment'!AZ63 |  | RiskCompound(D63,G63) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ64 | '3 - Risk Assessment'!AZ64 |  | RiskCompound(D64,G64) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ65 | '3 - Risk Assessment'!AZ65 |  | RiskCompound(D65,G65) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ66 | '3 - Risk Assessment'!AZ66 |  | RiskCompound(D66,G66) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ67 | '3 - Risk Assessment'!AZ67 |  | RiskCompound(D67,G67) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ68 | '3 - Risk Assessment'!AZ68 |  | RiskCompound(D68,G68) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ69 | '3 - Risk Assessment'!AZ69 |  | RiskCompound(D69,G69) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ70 | '3 - Risk Assessment'!AZ70 |  | RiskCompound(D70,G70) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ71 | '3 - Risk Assessment'!AZ71 |  | RiskCompound(D71,G71) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ72 | '3 - Risk Assessment'!AZ72 |  | RiskCompound(D72,G72) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ73 | '3 - Risk Assessment'!AZ73 |  | RiskCompound(D73,G73) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ74 | '3 - Risk Assessment'!AZ74 |  | RiskCompound(D74,G74) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ75 | '3 - Risk Assessment'!AZ75 |  | RiskCompound(D75,G75) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ76 | '3 - Risk Assessment'!AZ76 |  | RiskCompound(D76,G76) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ77 | '3 - Risk Assessment'!AZ77 |  | RiskCompound(D77,G77) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ78 | '3 - Risk Assessment'!AZ78 |  | RiskCompound(D78,G78) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ79 | '3 - Risk Assessment'!AZ79 |  | RiskCompound(D79,G79) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ80 | '3 - Risk Assessment'!AZ80 |  | RiskCompound(D80,G80) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ81 | '3 - Risk Assessment'!AZ81 |  | RiskCompound(D81,G81) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ82 | '3 - Risk Assessment'!AZ82 |  | RiskCompound(D82,G82) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ83 | '3 - Risk Assessment'!AZ83 |  | RiskCompound(D83,G83) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ84 | '3 - Risk Assessment'!AZ84 |  | RiskCompound(D84,G84) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ85 | '3 - Risk Assessment'!AZ85 |  | RiskCompound(D85,G85) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ86 | '3 - Risk Assessment'!AZ86 |  | RiskCompound(D86,G86) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ87 | '3 - Risk Assessment'!AZ87 |  | RiskCompound(D87,G87) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ88 | '3 - Risk Assessment'!AZ88 |  | RiskCompound(D88,G88) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ89 | '3 - Risk Assessment'!AZ89 |  | RiskCompound(D89,G89) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ90 | '3 - Risk Assessment'!AZ90 |  | RiskCompound(D90,G90) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ91 | '3 - Risk Assessment'!AZ91 |  | RiskCompound(D91,G91) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ92 | '3 - Risk Assessment'!AZ92 |  | RiskCompound(D92,G92) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ93 | '3 - Risk Assessment'!AZ93 |  | RiskCompound(D93,G93) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ94 | '3 - Risk Assessment'!AZ94 |  | RiskCompound(D94,G94) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ95 | '3 - Risk Assessment'!AZ95 |  | RiskCompound(D95,G95) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ96 | '3 - Risk Assessment'!AZ96 |  | RiskCompound(D96,G96) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ97 | '3 - Risk Assessment'!AZ97 |  | RiskCompound(D97,G97) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ98 | '3 - Risk Assessment'!AZ98 |  | RiskCompound(D98,G98) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ99 | '3 - Risk Assessment'!AZ99 |  | RiskCompound(D99,G99) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ100 | '3 - Risk Assessment'!AZ100 |  | RiskCompound(D100,G100) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ101 | '3 - Risk Assessment'!AZ101 |  | RiskCompound(D101,G101) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ102 | '3 - Risk Assessment'!AZ102 |  | RiskCompound(D102,G102) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ103 | '3 - Risk Assessment'!AZ103 |  | RiskCompound(D103,G103) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ104 | '3 - Risk Assessment'!AZ104 |  | RiskCompound(D104,G104) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ105 | '3 - Risk Assessment'!AZ105 |  | RiskCompound(D105,G105) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ106 | '3 - Risk Assessment'!AZ106 |  | RiskCompound(D106,G106) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ107 | '3 - Risk Assessment'!AZ107 |  | RiskCompound(D107,G107) |  | 0 | 0 | 0 | 0 | 0 | 0
Cell AZ108 | '3 - Risk Assessment'!AZ108 |  | RiskCompound(D108,G108) |  | 0 | 0 | 0 | 0 | 0 | 0